Technical Domain / Task Number 2	……4.3.3  (e-Navigation Risk Assessment)

Author(s) / Submitter(s)			Yves Desnoës…………………………………

e- Navigation risk assessment plan (draft)

# Summary

The paper contains a brief description of what a risk assessment plan would be and several annexes describing individual risks presented under a common format. It proposes on-going assessment and mitigation of risks in e- Navigation development and implementation from the point of view of IALA.

## Purpose of the document

It seems necessary to keep a central view of potential risks in the IALA domain, and propose actions for all IALA bodies including e-NAV/WG1. Some actions might need IMO decisions.

It is thus proposed to identify an owner within IALA committees for each of the identified risks, with a central body (to be decided) kept informed of developments and conducting an annual review of the different risks. The same working group could be tasked with several risk studies if they are strongly linked and some members, especially from the central body, could participate in several working groups.

## Related documents

G1 S1 to S3 of IALA’s Strategic Vision contribute to the following tasks of the SIP : T1 (HCD), T2( usability), T11 (SQA), T14( CMDS), T15( communications), T17( MSPs)t.

# Background

ENAV 15 identified in its report (paragraph 8.5) the need for a single repository for recording e-Navigation risks and their management plans. Risk analysis is a normal process in systems engineering an is the more useful when dealing with innovative projects.

# Discussion

Most risks described in the annexes are related in some way. Their proper management requires diverse skills and experiences which are too numerous for a global approach by one team only. For instance, the need for detailed specifications for interoperability (annex 3) might be seen as a consequence of the complexity risk (annex 1) and merged with it. But a system may be complex without interoperability problems and interoperability may be a problem between relatively simple systems ; annex 1 is mainly about structure and global architecture whereas annex 3 is about formalism which requires more expertise in data modelling and data management.

Risk register : why ?

Extracts from the SIP (NAV 59-6)

- S3: improved reliability, resilience and integrity of bridge equipment and navigation information (remark: part of it real time)

- S2: means for standardized and automated reporting

- S4: integration and presentation of available information ...

- IMO taking the lead in setting the performance standards appropriate for e-Navigation ... These standards should be based on user needs and should encourage technology neutrality and interoperability

- An infrastructure providing authorized seamless information transfer

  - Simpler for the mariner

  - More complex for the engineer

  - Development riskier for all stakeholders

Our goal is to establish a worldwide set of interoperable systems and products widely open to competition.

  - Our main tools are recommendations, guidelines and standards ; for interoperable parts, they must contain all necessary details, and that's a lot.

  - This makes us participants in the development process.

  - e-Navigation has no example to follow ; only “inspiration” from other projects.

  - In some way it is an extrapolation of ECDIS/ENC, AIS, VTS, ...

4        METHOD : RISK PORTFOLIO WITH A SEPARATE DOCUMENT FOR EACH RISK

The plan of a risk document is as follows :

- Identification of risk

- Description

- Rationale

- Likelihood

- Potential impact

- Mitigation measures

- List with entity in charge (owner)

- Description

- Schedule

- Progress indicator.

An annual review has to be planned.

5          TENTATIVE RISK PORTFOLIO

The risks which are underlined  are those which have been estimated the most pressing for the time being.

- Complexity  annex 1

- Quality deficiencies or excesses in the engineering process

Reliability

Availability

Maintainability

Security, including cyber-security

Validation/approval process.....

- Communications adequacy  annex 2

- Insufficient planning and configuration management of regulations and standards  annex 4

Phasing (defining stages, at least the first one)

- Need for particularly detailed specifications  for interoperability   annex 3

- Insufficient teamwork

- Over-specification, too many and/or too complex standards

# 6	  References

- ENAV15-16.1   Report of the 15th Meeting of the ENAV Committee

- ENAV15-6.1.1

THE STRATEGIC VISION FOR IALA for the period 2014-2026 (Approved by the IALA Council at its 56th session, 2013-12-11)

- NCSR1/9    Strategy Implementation Plan for e-navigation

# 7           Action requested of the Committee

The Committee is requested to:

- identify the “owner” of each risk deemed significant;

- task appropriate bodies under its purview to conduct the necessary analyses and propose mitigation measures;

- request the contribution of other IALA committees as appropriate;

- consider the possible involvement of other organizations in risk analysis.

Annex 1

Risk : complexity

Identification of risk

Description

e-Navigation implies interfacing a lot of existing and future systems which are not interfaced to this day. It also implies increasing the automation of several functions, some of which are performed manually. All this will drastically increase systemic complexity, including software complexity. Suitable methods have to be defined and their correct use verified in order to limit as much as possible complexity and the number of ensuing technical and operational problems.

Rationale

It is widely recognized that interoperability increases  technical and procedural complexity ; integration increases technical complexity.

"Distributed systems are becoming more complex in terms of both the

level of heterogeneity encountered coupled with a high level of dynamism of

such systems. Taken together, this makes it very difficult to achieve the crucial

property of interoperability that is enabling two arbitrary systems to work

together relying only on their declared service specification."

Moreover, this increase in complexity makes cost estimations less reliable, adding to the risk of deteriorating the image of e-Navigation.

"However, the complexity of interoperability and its multiple dimensions

make it difficult to understand the nature of the benefits, costs and trade-offs"

Likelihood

Very likely

Potential impact

Very high

The impact of too much complexity is a high defect rate.

If there are too many defects for too long in e-Navigation, its credibility could be jeopardized.

Mitigation measures

Develop a complexity dashboard based on a simple complexity model. See for instance "IT complexity: model, measure and master" by Commerzbank and CAPCO

entity in charge : IALA with the help of external experts for the initial stage

or voluntary nation or group of nations

Description

table of measurable quantities ;  to be studied and defined

Schedule

TBD

Progress indicator

- first, degree of achievement of the first version of the dashboard

- later on, dashboard

Aim for a first version of e-Navigation as simple as possible, based on tightly managed systems with a common target completion date ; high growth potential to be demonstrated

Compare with the european SWIM System Wide Information Management) project for air traffic management :

"Although the adoption will be gradual, a number of preliminary agreements are required and certain

minimum conditions need to be met. These are:

buy-in to the SWIM principles from the stakeholders;

an initial SWIM governance and management structure, including a legal framework;

....

initial set of defined SWIM profiles;

...

availability of initial infrastructure and a first set of deployed services compliant with the ...

..."

entity in charge : specific working group in IALA with the participation of IHO

description : specification of the services included in the first version ; configuration management of the specifications.

Schedule : ASAP

Progress indicator : degree of achievement of the specifications

Annex 2

Risk : Communications adequacy

Identification of risk

Description

There are a lot of existing systems for maritime communications, among which the GMDSS is prominent and they will exist for a long time. The AIS is also a sort of communications system and its fundamentals are not likely to change any time soon.

e-Navigation fora have not studied the communications in detail, probably supposing, rather implicitly, that available commercial communication networks, including satellites, would solve the matter. The maritime cloud concept seems to be the best illustration of that approach.

As e-Navigation will implement GMDSS functions, their interplay, even integration, has to be defined. As long as this is not precisely specified, the risk of miscarriage, or at least important delay, of e-Navigation is extremely high.

Rationale

Users are not going to pay twice for the same service, and they are not going to pay for transmission capacity which is now free of charge. Mandatory satellite links have to be tailored to the strictest need.

Besides, there are some areas where satellites signals are more difficult to receive, so that more traditional channels, mainly included in GMDSS, have to be used.

Communications as presented here are the support of technical interoperability (see annex 3). If communications are not properly designed and implemented, most e-Navigation goals cannot be achieved.

Likelihood

Very likely

Potential impact

Extremely high

Services without adequate communications would not be useful. Too expensive communications would not attract many users.

Mitigation measures

Conduct a dual approach of e-Navigation communications, with a bottom-up part describing what can be achieved with GMDSS (as existing and planned) in its different areas and a top-down part describing the maritime cloud plus GMDSS,  AIS, LRIT and other associated systems, as appropriate, and also describing what additional services they can support.

Entity in charge : IALA and IMO ; task group(s) to be defined

Description

-a/Identify existing GMDSS services to be adapted to e-Navigation and evaluate the corresponding traffic intensities.

-b/Define which sets of e-Navigation (portfolios or subsets of portfolios) services can be implemented where, how and with which operational priority, using GMDSS only, keeping in mind the goal of transparency to the user; extra capacity to be kept in order to keep automation under normal conditions.

-c/Compare with the maritime cloud as defined elsewhere

-d/develop a unified design

Schedule

TBD

Certainly on the critical path leading to e-Navigation

Progress indicator

- achievement of each ask a/ to d/ above

Annex 3

Risk : Need for particularly detailed specifications for interoperability (syntactic and semantic)

Identification of risk

Description

We choose to restrict the description of this risk to "high level" (in the meaning of layered models with the physical devices at the bottom) ones. The "lower layers" will be dealt with in the communications risk. This choice is arbitrary but corresponds to intuitive notions and helps bring some simplicity in a complex matter.

e-Navigation cannot work without complete detailed specifications for interoperability, inter alia those aimed at in the title above. These detailed specifications will be represented by the S 100 registry and by some detailed specifications of services, for instance basic services categories as defined in  :

"enav15_8_11_appendix_01_basic_service_categories_definitions_etc_rec_genericserviceengmodel_v0_06_20140812".

e-Navigation could also imply interfacing  systems to exchange/share the data/information which may be stored in these systems in different ways. In particular, these data to be exchanged could have been stored without using a systematic approach for identification, assessment and management of information security risk  (in this regards, confidentiality, integrity and availability of data should be considered as critical factors), and that's part of semantics (exhaustive definition of information).

As there seems to be little work by experts on defining which specifications at which level of detail are really needed, there is a high risk that they be incomplete and contain discrepancies and redundancies.

Rationale

Let's just quote a recent report produced in the frame of a European project.

" No solution attempts to  resolve all five dimensions of interoperability  ....

The CONNECT project, an initiative funded under the Future and Emerging

Technologies programme within the ICT theme of the European Commission’s Framework programme, is taking a novel approach to the study of interoperability in  complex distributed systems, going back to basics, and taking input from a variety of  sub-disciplines including the middleware and semantic web communities, but also  looking at supportive areas such as formal semantics of distributed systems, learning and synthesis technologies and support for dependable distributed systems.

.....

This chapter has investigated the problem of interoperability in the complex distributed systems of today, with the added complexity stemming from the extreme level heterogeneity encountered in such systems coupled with the increasing level of dynamism of such systems which results in the need for spontaneous communication.

The chapter highlights the key barriers to interoperability coupled with a discussion of solutions to interoperability featuring the research in the middleware community and related research on semantic interoperability. The most striking aspect of this study is that, while both communities focus on key interoperability problems, research efforts have to a large extent been disjoint. The other striking feature is that, despite considerable research efforts into interoperability dating back to the early 1980s, this remains a poorly understood area and currently solutions simply do not meet the needs on the complex distributed systems of today, particularly in terms of the levels of heterogeneity and dynamism as mentioned above."

There is currently no recognized method to produce complete and non-redundant specifications for interoperability.

Likelihood

Very likely

Potential impact

Very high

Mitigation measures

Create a team of experts in interoperability tasked with studying existing and planned specifications for interoperability and proposing a method adapted to e-navigation, to its environment and to its goals and aiming at ensuring that the specifications of interoperability are correct and limited to the need.

Entity in charge : IALA and IHO under the aegis of IMO

Description

-  Firstly, on the basis of available knowledge, design a first version of a standard set of rules and constraints that will guarantee highly reliable interoperability modes, bearing in mind the goal of simplicity set elsewhere.

Among other rules, good practices in terms of information security management for e-navigation (and procedures in order to be sure that these practices are properly implemented) should be established.

-  Later, study and design evolutions to this standard, possibly adding complexity in a prudent way.

Schedule

TBD

Progress indicator

- degree of achievement of each version of the standard

Annex 4

Risk : Insufficient planning and configuration management of regulations and standards

Identification of risk

Description

The development of e-Navigation as it is imagined today consists of developing numerous interoperable systems, many of them being competing products. In order to obtain a consistent set of harmoniously interoperating products and systems, clear and unambiguous specifications must be made available to all interested stakeholders in a timely and organized manner. These specifications have a life cycle which must be defined and managed as early as possible, and much progress is needed to that aim.

Rationale

The S 100 registry in itself will not be sufficient. Its capacity to evolve continuously is also a risk for interoperability and well defined procedures are needed to plan official versions and to handle changes. The services constituting e-Navigation will have to be defined in all details necessary for their use by other products, in an interoperability paradigm ; here too official versions will be necessary and will have to be planned and any changes (in systems engineering, nothing can be completely frozen for a long time)  managed. There will also be the issue of compatibility of successive versions with other versions of the same products and of other ones.

One could think that that kind of detail is exclusively an industrial task. Such a view does not correspond to reality, which is that interoperability and interoperation modes will have be completely defined by the international public organisations (mainly IMO, IALA, IHO, IEC, ISO, ITU), taking into account users needs and industrial inputs.

Suppose some companies want to develop competing systems to manage and deliver MSI, charts and nautical publications as global packages. If we want competition to be successful, we have to plan the issuance of associated official

Likelihood

Likely

Potential impact

Very high

Mitigation measures

Define a method for planning and configuration management for IALA e-navigation services.

Entity in charge : IALA and IHO under the aegis of IMO

Description

Establish a list of “configuration items” which are the standards and standard-like objects which will be necessary and sufficient for the first set of deployed  services (see annex 1) of e-Navigation”.

Study the existing procedures (S 100 in particular) in the light of existing general standards on planning and configuration management, e.g. ISO/IEC 12207.

Propose an organization for planning and configuration management of configuration items.

Schedule

2016

Progress indicator

- report

Interoperability in Complex Distributed Systems - Gordon S. Blair, Massimo Paolucci, Paul Grace, Nikolaos Georgantas  - 2011

http://www.rand.org/content/dam/rand/pubs/monograph_reports/MR1235/MR1235.chap2.pdf

http://edmcouncil.org/downloads/MC_CAPCO.IT.complexity.Model.measure.pdf

SWIM Concept of Operations - Eurocontrol - 10th june 2013

We separate technical interoperability from syntactic and semantic (including dynamic aspects) interoperability. In the ISO/OSI model, the first one consists approximately of the 4 lower layers, up to "transport", the two others being  implemented in the three upper layers ; this is approximate because IMO has not chosen a model yet, so that those definition will certainly have to evolve.

note from author : discovery of services, data, middleware, application, non-functional

Interoperability in Complex Distributed Systems - Gordon S. Blair, Massimo Paolucci, Paul Grace, Nikolaos Georgantas  - 2011