IALA VTS MANUAL

PRODUCTION OF NEW EDITION FOR PUBLICATION IN 2008

(for review and discussion at VTS20)

Introduction

The current edition of the IALA VTS Manual was drafted in 2001 and published in March 2002.  Its successor edition is now planned for release in early 2008.  To achieve this date the VTS Committee approvals process will need to complete by September 2007 (VTS 27).

It is intended to restructure the Manual to encompass all aspects of recent VTS development and to provide guidance and a benchmark of best practice.  It will be designed as a textbook to appeal to the widest possible readership amongst the profession, and should be relevant at individual, corporate and authority levels.

Co-ordinator

Geoff Eades has been nominated as the co-ordinator for the project and will act on behalf of the VTS Committee as the editor of the Manual.   The VTS Committee will approve the contents of the Manual before its submission to Council.

The Proposed Structure

A new chapter structure has been devised which is at Annex A.  The aim has been to:

- Provide comprehensive guidance on all aspects of VTS, relying on reference to other published material for the more detailed advice or instruction.

- Where possible, the subject matter has been matched to the responsibilities of a single Working Group (WG) in an attempt to reduce the co-ordination task.

- Avoid chapter lengths that are either over-long or too short.  Where risk of this occurs consideration will be given to either amalgamating short chapters or dividing long chapters where appropriate.

Under each chapter heading is a suggested breakdown of the broad contents of each chapter.  At this stage this has been added to provide an idea of the shape and form of each chapter.  It will be for the WG responsible for drafting a chapter to determine its optimum contents and to agree this with the VTS Committee.

Grouping of Chapters into Sections

It will be noted that the chapter headings have been grouped into three sections:

- Section 1  	VTS - Regulatory Framework and Functions (Chapters 1 to 5)

- Section 2  	Establishing and Staffing a VTS (Chapters 6 to 12)

- Section 3 	Conduct and Management of VTS Operations (Chapters 13 to18)

It is for consideration that these sections should form three separate volumes of the IALA VTS Manual.  They could be published individually as fully self-contained bound documents, and a guard cover provided to house the three volumes into a single book.   The main advantage of this course of action would be to stagger authoring and publication effort and, particularly for the future, to spread the updating and editing tasks when revising the manual.

Revision Plan

A draft plan setting out the revision task is at Annex B.   A suggested schedule for authoring, editing, printing, checking and publishing the material is based on the proposal for a three-volume manual.  If a single volume manual is decided upon some modification to this plan would be feasible, but scope to do so would likely be limited by the need to avoid overloading the WG's work programs.

It has not been possible to take into account other work commitments for which each WG is responsible so it will be necessary to confirm at VTS 20 that WG Chairman are content with the planned tasking.

REQUIREMENT

The VTS Committee is invited to:

- Agree the IALA VTS MANUAL revised chapter structure and the Chapter Titles

- Agree the broad chapter contents, recognising that WGs may wish to enhance or modify the content during the revision process

- Agree, in principle, the publication of the Manual as a multi-volume publication. (Subject to other considerations outside of the VTS Committee remit)

- Agree the Revision Work Plan and incorporate it into the VTS Committee Work Program

Delegates will be requested at the opening Plenary Session of VTS 20 (Monday, 2 February 2004) to provide their agreement, or alternative proposals, on the topics listed above to enable WGs to progress planned work during the course of the Hong Kong meeting.

Annexes:	A. 	Proposed Chapter Structure for 2008 Edition

B.	Revision Work Plan

Annex A

IALA VTS MANUAL

PROPOSED CHAPTER STRUCTURE FOR 2008 EDITION

SECTION 1:	VTS - REGULATORY FRAMEWORK AND FUNCTIONS

Chapter 1 		Introduction to VTS

Purpose of the Manual

Organisation and Consultative Bodies concerned with VTS

Development of VTS - A Brief History

Annex A:   Definitions

Annex B:    Glossary of Abbreviations

Chapter 2		Legal Framework

International Law

IMO Conventions, Resolutions and Guidelines

National Law

`		Harbour/Port Byelaws and Regulations

Authority

Liability

Environmental Law

Chapter 3		Regulation of VTS

IMO resolution Guidelines for VTS

IALA

Other regimes - EU

National

The need for common approach to standards

Chapter 4 		The Functions of VTS

Risk Reduction, Risk Management

Safety of Maritime Traffic

Efficient Vessel Traffic Flow

Efficient management of Port resources

Protection of the Marine Infrastructure

Protection of the Environment

Security in  the Maritime Domain -Its impact on VTS

VTS in an inter-modal transport system

Chapter 5		Types of VTS  - Requirements and Considerations

Offshore, International Waters and

Waterways governed by Treaty

Coastal Waters

Harbour approaches, anchorages and Ports

Rivers Canals, confined waterways

Ports of Refuge - Implications for VTS

SECTION 2		ESTABLISHING AND STAFFING A VTS

Chapter 6		Determining the Need for A VTS

Needs Analysis

Hazard Identification

Risk assessment

Risk Control Options

Cost/benefit Analysis

Categorisation of VTS

Chapter 7 		Planning and Organisation of a VTS

Area limits, boundaries, separation zones, shipping lanes.

Prohibited or Dangerous areas, safety zones (place of safety), anchorages

Traffic management, TSS, Separation Criteria

Pollution Control

Surveillance and Monitoring

Enforcement, Control, Direction (definitions/Difference)

Contributory and Participatory Navigation Assistance

Advice and Information Services

Infringement of Regulations.  Accident avoidance.

Pilot/VTS interface.  The role of Pilots in a VTS

Chapter 8 		Procurement Considerations

Procurement Process:

Requirements capture

Feasibility studies and project definition

Options

Development, manufacture, installation and acceptance.

Demonstrators and modelling.

Project Management:

Management plan

Quality

Project risk plan

Scheduling

Acceptance testing

International Standards

Human factors

Chapter 9		VTS - Equipment

Sensors		Radars

Transponders

Communications DF

Optical, TI, LL devices

AIS

Data Displays; Symbology

Sensor Co-ordination 	Track combining

Track Table

Traffic Image

Communications 	Voice HF/UHF/VHF

EDI/e-mail

Telephone/Fax/Telex

INMARSAT

Tidal Data		Tidal stream model and display

Depth of water/ height of tide model

Dynamic safe-depth (UKC) model

Pilot aids - carryaboard equipment

Meteorology Data Sensors

Visibility sensors

Control Room, operation workstations and sub systems

Database management systems

Standards, Accuracy, Quality.

Chapter 10 		VTS Personnel

Key personnel - ashore and afloat

The Ships Captain

Pilot

VTS

Captain/Pilot/VTS relationship

VTS Manager

VTS Superviser/Watch leader

VTS Operator

VTS Centre - watch organisation

Functions, duties & tasks

Delegated responsibilities.

Chapter 11		Qualification and Training of VTS Personnel

International Framework - STCW

Recruitment, Training and Certification

Model Courses

Refresher training and validation.

Chapter 12		Principles of Traffic Management

Development of safe standard operating procedures

Principles of safe waterspace and traffic management

Two-way and one-way traffic occupancy; channel width, length, points-of-no-return, ship size and manœuvrability.

High-risk ships and cargoes

Risk induced by geography and hydrography

Other factors that can increase risk.

Allocation of waterspace. Slot management

Authorisation of ship movements, allocation of priority

Provision of navigation assistance

Traffic organisation service

Shore based Pilotage

SECTION 3  		CONDUCT AND MANAGEMENT OF VTS OPERATIONS

Chapter 13		VTS Information and its Promulgation

It was proposed that this chapter should be a template from which VTS authorities could construct their own data sheets of information needed in the VTS centre and made available on the web.  Methods of Promulgation.

Chapter 14		VTS Procedures - General

Data acquisition, reports, reporting points.

Identification.

Development of Traffic image

Traffic organisation and management.

Monitoring and authorising traffic movements

Passage Plans; exchange electronically

Detection of unsafe/unauthorised operations:

Infringements of exclusion zones

Infringements of separation intervals

Provision of support services

Relationships with Pilots and Ship's Masters

Chapter 15		VTS Procedures - Emergencies

Roles, responsibilities, pre-planned responses and co-ordination with other agencies in the general event of accident/emergency and specifically including:

Collision

Stranding

Fire on-board

SAR

Oil spill

Sinking

Hazardous cargo incidents

Terrorist action

Procedures for dealing with a disaster (eg fire) or malfunction of the VTS and its equipment

Chapter 16		Administrative Requirements for Operating a VTS

Co-ordination and planning of local resources.

Liaison with allied services

Agents

Customs

Security agencies

Quarantine

Auto-billing

PEC

Chapter 17		Archives and Records

Required to assist:

Re-construction of marine incidents

Litigation

Administration (Chapter 16)

Shipping , masters, pec data.

Chapter 18		Public Information

Public awareness, development of public image of VTS

Routine dealings with press and media.

Procedures for handling media following accidents and emergencies.

Annex B

IALA VTS MANUAL - DRAFT REVISION WORK PLAN FOR 2008 EDITION

(For discussion and agreement at VTS 20)

| Chapter No. | Title | Author | Initiate Drafting | Draft for Circulation to VTS Committee | Final version to Committee for agreement | Proof read | Available to print |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Foreword | Editor | VTS 24 | VTS 25 | VTS 26 | By December 2005 | January 2006 |
|  | Preface | Editor | VTS 24 | VTS 25 | VTS 26 |  |  |
| 1 | Introduction to VTS | Editor | VTS 20 | VTS 21 | VTS 22 |  |  |
| 2 | Legal Framework | Editor | VTS 21 | VTS 22 | VTS 23 |  |  |
| 3 | Regulation of VTS | Editor | VTS 21 | VTS22 | VTS 23 |  |  |
| 4 | Functions of VTS | WG1(+ 2/3) | VTS 20 | VTS 21 | VTS 22 |  |  |
| 5 | VTS Types | WG1 (+2/3) | VTS 21 | VTS 22 | VTS 23 |  |  |
| 6 | Determining the need for a VTS | WG1 & 2 | VTS 20 | VTS 22 | VTS 24 | By June 2006 | July 2006 |
| 7 | Planning and Organisation | WG 1 | VTS 20 | VTS 22 | VTS 24 |  |  |
| 8 | Procurement Considerations | WG2 | VTS 22 | VTS 23 | VTS 24 |  |  |
| 9 | VTS Equipment | WG2 | VTS 20 | VTS 22 | VTS 24 |  |  |
| 10 | VTS Personnel | WG3 | VTS 21 | VTS 22 | VTS 23 |  |  |
| 11 | Qualification and Training | WG3 | VTS 22 | VTS 23 | VTS 24 |  |  |
| 12 | Principles of Traffic Management | WG1 | VTS 22 | VTS 23 | VTS 24 |  |  |
| 13 | VTS Information | WG1 | VTS 23 | VTS 24 | VTS 25 | By November 2007 | December 2007 |
| 14 | VTS Procedures - General | WG1 | VTS 24 | VTS 25 | VTS 26 |  |  |
| 15 | VTS Procedures - Emergencies | WG1 | VTS 25 | VTS 26 | VTS 27 |  |  |
| 16 | Administrative Requirements | WG3 (+2) | VTS 24 | VTS 25 | VTS 26 |  |  |
| 17 | Archives and Records | WG2 (+1/3) | VTS 24 | VTS 25 | VTS 26 |  |  |
| 18 | Public Information | WG3 | VTS 25 | VTS 26 | VTS 27 |  |  |
| Annex A | Definitions | Editor | VTS 25 | VTS 26 | VTS 27 |  |  |
| Annex B | Glossary of Abbreviations | Editor | VTS 25 | VTS 26 | VTS 27 |  |  |

Notes:

1.	VTS 20 	Mar 2004			VTS 23		Sep 2005			VTS 26		Mar 2007

VTS 21		Sep 2004			VTS 24		Mar 2006			VTS 27		Sep 2007

VTS 22		Mar 2005			VTS 25		Sep 2006