Chapter 9 		Procurement Considerations

Procurement Process:

Requirements capture

Feasibility studies and project definition

Options

Development, manufacture, installation and acceptance.

Demonstrators and modelling.

Development and Procurement

Before considering the establishment of a new VTS or the enhancement of an existing VTS, the Competent Authority and/or future VTS  Authority should launch a Feasibility Study, which should contain the following five phases, in which the Risk Management process steps are addressed:

Inception phase

Feasibility and Design Study phase

Risk Assessment phase

Cost/benefit phase

Implementation phase

Evaluation phase

The activities to be undertaken in each phase are shown in Figure 2

INCEPTION

Problems

Constraints

Area

Traffic Management

Tools

Evolve options

Weightings

Importance

Risk

Organisation

Framework

Structure

Legal

Security

Funding

Operational objectives

Areas

Sub Area

Sub Area

Delineate areas

Measures to be taken

Determine level of service

FEASIBILITY AND

Functional Requirements

Functional Specification

Traffic Management Measures

Finalise Inception Proposals

Outline Procedures

Manning Training

Cost/Benefit analysis (preliminary)

…DESIGN STUDY

Geotechnical Data • Project Plan

Resource Allocation • Spend Profile

Timescale • Design Review/Audit

Equipment Technical Specification

Civil

Mechanical

Electrical

IT Hardware/Software

Training

RISK ASSESSMENT

Navigational Risks:

• Environmental Risks

FSA Techniques

Estimation

Evaluation

Alternative mitigation measures

Estimated reduction

COST/BENEFIT

Analysis-Investment v risks reduction

Direct benefits

Indirect benefits

Prospects

Value Added Services

IMPLEMENTATION

Implement other traffic management measures

Preparation • Tender procedure

Purchasing           • Building

Legislation/organisation/personnel   • Trial operations

EVALUATION

Technical Performance

Operational Performance

Operational Objectives

Problems alleviated

Not acceptable               Acceptable

Figure 2  Main activities of the various phases in the development and procurement of a VTS

When considering the implementation of a VTS, the Government or the Competent Authority should take full account of IMO Assembly Resolution A.857(20) on Guidelines for Vessel Traffic Services (see Annex 1) and, in particular:

1	ensure that legislation is in place for the establishment and operation of a VTS, in accordance with national or international law;

2	ensure that a mission statement and objectives for the VTS are set;

3	ensure that a VTS Authority is appointed and legally empowered;

4	ensure that the geographic service area is delineated and declared a VTS area; including, where appropriate, defining VTS sub areas and sectors;

5	determine the services to be provided by the VTS with regard to the objectives of the VTS;

6	establish appropriate standards for shore and offshore based equipment

7	ensure that the VTS authority is provided with the equipment and facilities necessary to effectively accomplish the objectives of the VTS;

8	ensure that the VTS Authority is sufficiently staffed with appropriately qualified, suitably trained personnel capable of performing the tasks required;

- instruct the VTS Authority to operate the VTS in accordance with relevant IMO resolutions.

In addition the Competent Authority will need to decide whether the VTS Authority has sufficient technical competence in house to undertake the detailed planning of the intended service.  Where the VTS Authority does not have such competence immediately available use should be made of external expertise.  When employing external expertise care should be taken to ensure that the persons/companies involved are independent and impartial. It should also be noted that the expertise to describe the system is different from the expertise required to supervise the implementation and the quality requirements of the system.

Broadly the expertise required can be considered as falling into the following three categories:

- clarifying the objectives;

- describing the system;

- supervising construction of the system, including effective quality control.

### Inception phase

The Inception Phase should answer the question of whether active traffic management is the appropriate means to address the local traffic problems. Active traffic management should only be used in those areas where other means are inadequate to provide the desired level of safety and protection of the environment. This section gives guidance on how the Inception Phase should be conducted. The reports of the Inception and Feasibility Study Phases together are sometimes referred to as the Baseline document.

In the Inception Phase, all relevant problems in the maritime area concerned should be defined and analyzed. Further, as a second step in the process, operational objectives should be established with the ultimate aim of alleviating the defined problems. The last step in this phase is to identify the most appropriate traffic management tools, in terms of effectiveness and costs, to alleviate the defined problems. Implementing the rather expensive VTS tool may be one of these solutions.

The possible local traffic problems could be related to:

- The interaction of maritime traffic,

- Volume and mix of traffic;

- The local conditions like geography, hydro/meteo, tides and weather;

- Protection of the marine environment; and

- Protection of the surrounding area.

In addition, future developments in the port infrastructure and the resulting changes in traffic volumes and composition, including dangerous cargoes and any other relevant future development in the area concerned should be considered in this phase.

In the specific case of a Coastal VTS, future trends in traffic volume and other activities in the coastal area, such as fishing, recreation and offshore activities should be taken into account.

Further developments in VTS technology and SOLAS requirements for navigational and communication equipment on board vessels should be considered as well.

Furthermore in the case of a decision to establish a VTS, the following aspects need to be addressed;

- Organisational framework of the national and local maritime authorities in relation to implementing new traffic management solutions, VTS in particular; and

- The present regulatory or legislative framework, including local by-laws, rules and recommendations. Special attention has to be devoted to ascertain any requirement for adjusting the framework to allow for effective implementation of a VTS.

Attention is drawn to IALA Recommendation V-119 on the Implementation of Vessel Traffic Services, which provides a comprehensive list of all the relevant items to be addressed.

### Feasibility and Design Study Phase

- If the previous Inception Phase has indicated that just passive measures are inadequate to attain the desired level of safety and efficiency of the maritime traffic, in the area under consideration, the effect of establishing a VTS should be tested.

- The foundation for the work in the Feasibility and Design Study Phase is the approved report on the Inception Phase and the expected functions and benefits of a future VTS. This input may also give an indication of the desired level of service to be provided by the VTS.

The overall objective is to produce a system that meets exactly the requirements of the VTS Authority, and against which the design can be validated fully, verified and tested before development.  There are normally two levels or sub-phases in defining the requirements of a VTS, these are:

- the development of an overview of the system and an intermediate level of detail about the system’s function, operation and environment, referred to in this Chapter as the feasibility sub-phase; and

- the development of the detailed technical specification of requirements, referred to in this Chapter as the technical specification sub-phase.

The factors that need to be considered are described briefly in the following paragraphs:

#### General

One of the main tasks of this Phase is to establish the functional requirements for the VTS. The Competent Authority needs to assess the types of vessels using a particular area, the requirements to aid their safe and expeditious passage, the operational benefit of a VTS and the broad implications of providing the service.   These considerations should take into account the existing aids to navigation and traffic routeing schemes in the area concerned.

This Phase is of critical importance to the establishment of a VTS optimised for the area that it will cover and it is essential that the correct balance of input by the VTS Authority, users, local services and allied services is achieved. Examples of some of the functional requirements that need to be taken into account are listed below.

#### Delineating the VTS Area

  - Local Geography.   The local geography will be the determining influence on the size of the area to be covered by a VTS.  In the case of ports these vary enormously in their geography.  Some ports, are extremely simple and are little more than an indentation in the coast protected by breakwaters.  Entry and exit is through a passage between the breakwater heads, which give direct access to the open sea.  Vessels are only restricted in their freedom to manoeuvre as they pass through the breakwater and into the port itself.  At the other extreme are estuarial ports, often far from the open sea with long approaches encumbered by shallow, shifting sandbanks.  Vessels using these ports will be restricted navigationally and possibly be unable to anchor or reverse course over long stretches of their passage.

  - Local Conditions:  The prevailing weather, in particular visibility and wind together with the tidal range and stream, may impose difficulties on the ability to navigate safely.  Together with the local geography they determine the degree of navigational difficulty likely to be encountered by a vessel.

An appreciation of these physical factors, plus any interface with local or regional services, leads to a first assessment of services which would be of most benefit to vessels navigating in the area.

  - Numbers of vessels and types:  The numbers of vessels, including local traffic, and their type is significant.  A simple count of vessels, although of value, is not sufficient.  The vessels need to be considered with regard to their size, type, equipment, manoeuvrability, spatial distribution and cargo so that the optimum service meeting the needs of all users and without placing unnecessary constraints on the movement of any of the vessels can be identified.

  - Commercial factors:  Any VTS must make due allowance for any potential conflict between safety and commercial operation and pre-empt such conflicts before they arise.  Ports must operate in an efficient and timely manner and meet the needs of their users, but this must be done without impinging on the safe operation of the port.  The distribution of ship arrivals and departures may be an important factor influencing the port management resources.  Unannounced arrivals and departures can have a considerable and adverse effect on the viability of a port.  Some ports, such as ferry ports and container terminals, operate to a schedule which has to be maintained in virtually all weathers.

  - Other Activities: Naval operations, oil and gas production and recreational activities may take place within the area to be covered by a Vessel Traffic Service.  These activities will also influence the operation of the scheme and must be taken into account.  A good working relationship needs to be established and maintained with other users of the area.

#### Environmental Aspects

Many incidents in recent years have highlighted the hazard to the marine environment presented by large tankers and other vessels carrying dangerous substances and has drawn political attention to VTS, ship reporting systems and vessel identification.  As a consequence of these incidents protecting the environment from marine casualties has attracted significant public attention from outside the marine industry.  It may be that pressures to protect the environment will continue to grow, causing a change in the balance between efficiency, safety and the environment.  Annex 3 contains further guidance on the role VTS can play in the protection of the environment.

There are areas where the consequences of an incident would be such that extra safety provision, over that normally applied, may be appropriate.  These areas must be identified so that the VTS can accommodate them.  In this context, suitable measures may include routeing vessels clear of environmentally sensitive areas and the careful organising of traffic flow, so that vessel numbers in particularly sensitive areas are limited.

A VTS will also need to take account of, and probably operate in conjunction with, mandatory ship reporting systems which have been adopted by IMO and are completely or partly within the VTS area.

#### System users and user requirements

In any consideration of VTS the views of the various users must be included.  In the past a VTS was designed primarily to meet the immediate needs of vessel operators.  As VTS grew and became recognised as a valuable information gathering and processing resource, the list of users of Vessel Traffic Services expanded to include many in the shore-side marine industry.

While the benefit to the shipping community is tangible and immediate, the public benefits as well.  The VTS Authority must consider the collective, and at times conflicting, needs of these entities when designing and operating a VTS.  The following list, by no means exhaustive, identifies a number of potential users and participating bodies.

###### MaritmeUsers

Commercial vessels of all types 	       Support vessels (buoy tenders, tugs, dredgers)

Fishing vessels				       Recreational vessels

Military or other public vessels		       Regatta or racing vessels

Aircraft (amphibious, seaplanes and helicopters)

###### Allied Services, Port Operations & Adjacent VTSs

Pilotage Service, Tugs and linesmen	Other VTS		Terminal Operators

###### Emergency Services

Search and Rescue	Fire Service		Pollution Control

Other agencies which could be involved

Terminal Operators			Foreign Governments (Flag State)

Port State Control			State or Municipal Governments

Shipping Agents				Customs

Immigration				Shipyards

Industry or Trade Organisations		Environmental Organisations

Persons living along the waterway	International organisations

Media					Quarantine services

The feasibility and design study phase is also intended to provide a VTS Authority with a framework for proceeding further with development against carefully established guidelines of requirement, cost, risk and time.  It should comprise some or all of the following:

- Description of the constraints and context in which the VTS will operate;

- Evaluation of the technology available and determination of  the standards to be used;

- Evaluation of the human resources needed for operation of the system and consideration of manning levels, training and skills required;

- Evaluation of the health and safety facilities needed to safeguard staff and other persons associated with the VTS system;

- Preparation of a management plan for the entire development;

- Assessment of the method, or methods, to be used for Quality Assurance;

- Assessment of the probability that the VTS system will be developed, installed, tested and ready for operational use within both the required time scale and the available financial resources;

- Development and evaluation of system design options

- Determination of the Integrated Logistic Support (ILS) requirements, including the identification of the through-life elements of the system and the means for achieving enhancement and upgrades;

- Evaluation of a Cost-Benefit analysis and the identification of any trade-offs.

The feasibility sub-phase should identify the range of activity that will need to be examined during the technical specification sub- phase, show the feasibility of any actions suggested and eliminate high-risk elements.

On satisfactory completion of the feasibility sub-phase the VTS Authority will be in possession of a highly detailed basis for proceeding to technical specification phase with confidence that its outcome will provide a viable solution for developing the system.

Attention is also drawn to IALA Recommendation V-119 on the Implementation of Vessel Traffic Services, which provides a comprehensive list of all the relevant functional requirements to be addressed within the feasibility sub-phase

#### Technical specification sub-phase

The Technical specification sub-phase should produce the definitive statement of how the system, including and buildings, is to be constructed, and how sub-systems and components should interact with each other to produce a viable VTS.  It may be necessary to investigate thoroughly any proposed solutions in areas of technical difficulty or high risk to ensure that they are likely to be effective.

This sub-phase should produce a comprehensive design for the overall VTS, including the performance criteria and technical specifications for the purchase of equipment and the definition of the interface standards that need to be met.  The technical specifications should be prepared to such a level that they can be used in the procurement documentation and should include clearly defined acceptance and testing programmes.

A detailed project plan for the design, manufacture/construction, installation and commission stages should be prepared and any tasks or items having a long lead time or which may be difficult to obtaining should be identified.

### Risk assessment phase

The Risk Assessment Phase is intended to confirm that the measures being designed and introduced will reduce the risk of collisions and groundings in the area to a level considered by the Competent Authority to be satisfactory.

The risk level should be calculated by taking into account:

- The type, size, speed, manoeuvrability, routes and spatial distribution of ships  using the area, including local craft;

- The types of aids to navigation provided in the area and their locations; and,

- The traffic routeing schemes in use in the area.

The total risk equation comprises the Probability, or frequency, of an incident occurring, the Consequences of an incident and the Governmental or public Acceptability of such an incident.  The risk assessment should identify and quantify each of these aspects.

IALA Guidelines on Risk Management (June 2001) outline a general risk assessment and risk management methodology for Marine Aids to Navigation including Vessel Traffic Services (VTS) so that all types of risks can be effectively managed.  The Guidelines may be used when assessing the optimum mix of aids to navigation, including VTS, for mitigating risk.

### Cost/ benefit phase

After completion of the Design and Risk Assessment Phases, a cost benefit analysis could be carried out to determine whether the expected reduction in risk is justified in terms of the level of investment required.

Both the additional direct and indirect benefits and prospects that a VTS might offer, including additional value added services for the traffic in the future as well as the benefits to shore based port operations, should be taken into consideration.

A direct benefit that could be taken into consideration, amongst others, is the probable reduction in other waterway infrastructure costs that may arise from implementation of the changes, such as replacing labour intensive processes using traditional equipment with more modern equipment and automated processes.

Indirect benefits should include an estimation of costs that would otherwise have been incurred in the event of an incident/accident, based on the projected difference between the frequency of occurence of such incidents/accidents before and after implementation of any changes.

Further guidance on cost/benefit analysis is given in Annex 2 of this Manual and in IMO MSC/Circ.829 & MEPC/Circ.335 of 17 November 1997 on “Interim Guidelines for the Application of Formal Safety Assessment (FSA) to the IMO Rule-making Process”.

### Implementation phase

The main tasks during the Implementation phase will be associated with the:

- preparation and publication of tenders to carry out the construction and installation of the equipment and any construction or alterations to buildings;

- evaluation of tenders and awarding of contracts;

- monitoring of progress of the contracted work; and,

- verification or conduct of tests on individual items of equipment of sub-systems

While it can be expected that individual items of equipment will have been tested before installation, during this phase the system should be tested as an entity.  This should include the integration of VTS Personnel and therefore implies that the recruitment and training programme should be conducted before final acceptance of the system is undertaken.

All documentation necessary for the proper operation of the VTS, including operational rules, procedures and contingency plans, should be developed during this phase. In addition, all national and international administrative and legal matters concerning the establishment and operation of the VTS should be resolved, including the availability of radiocommunication frequencies and, if necessary, the approval by IMO for any traffic routeing schemes or ship reporting systems.

This phase will be complete when the VTS has satisfactorily finished all necessary testing and trials and has full operational capability.

### Evaluation phase

The Evaluation phase is intended to ascertain the effectiveness of the VTS in meeting its design target with respect to mitigating the risks of collisions or groundings in the area concerned.	Wherever practicable, the evaluation should take place after experience has been gained by the VTS personnel in the use of the equipment and practical operation of the service.

An overall evaluation of the VTS should be preceded by an assessment of the effectiveness of:

- the technical equipment and sub-systems integrated together to form the VTS technical system; and,

- the operational use of the VTS technical system as a traffic management tool in the area concerned.

If this phase indicates that the VTS is less effective than its design target, the reasons for this should be investigated and if necessary modifications made to the system to improve its operational effectiveness.

Project Management:

Management plan

Quality

Project risk plan

Scheduling

Acceptance testing

International Standards

Human factors