VTS Committee – Revised Work Programme 2002-2006

Revised at VTS22 Chairmans’ Meeting, March 2005

| Task | Estimate No. of Sessions | Comments | Working Group |
| --- | --- | --- | --- |
| - Review - VTS Manual - IMO Guidelines on VTS | 5-6 | See note 1 | Ops, Tech, Personnel & Training (P&T) |
| - Develop a draft IALA Vision of the Future for VTS | 3-4 | Complete VTS19 | Ops |
| - Develop a recommendation on the performance requirements for VTS equipment. | 4-5 |  | Ops/Tech |
| - Develop a recommendation on generic operational procedure for VTS | 2-3 | Complete VTS21 | Ops |
| - Develop Guidelines for the application of internationally adopted symbology for use in VTS centres and co-ordinate with IEC. | 4-6 | Complete VTS21 | Ops, Tech |
| - Develop Guidelines for the technical specification of VTS equipment | 4-5 | Radar Completed VTS20 | Tech |
| - Develop guidelines on data exchange between VTS system. | 4-5 |  | Tech |
| - Develop Guidelines on Staffing Levels at VTS Centres - collect information on staff levels in accordance with service levels - develop guidelines on approaches to VTS Operator Workload Staffing Levels | 5-6 |  | P&T |
| - Consider Refresher Training for VTS Personnel – As Per Council report 34 – Review of V-103 (D1-3) brought forward. | 3-4 | Completed VTS21 | P&T |
| - Finalize Guidelines on Categorization of VTS / VTS Risk Mitigation | 2-3 | Completed VTS21 | Ops |
| - Review IALA VTS documentation to ensure Security Issues are addressed where appropriate. | On going | Following IMO ongoing work Discuss with PAP | Ops, Tech, P&T |

Monitoring Items

| M1 Monitor the use by members of the IALA Guidelines on Risk Management as applied to VTS | Continuous | Rapporteur see note 2 |
| --- | --- | --- |
| M2 Monitor the impacts of AIS on VTS staffing and training | Continuous | Rapporteur see note 3 |
| M3 Monitor the work of PIANC, WG24 | Continuous | Rapporteur See note 3 |
| M4 Monitor developments in aspects of ‘Navigational Assistance’ as it relates to pilotage. | Continuous | Rapporteur See note 3 |

Deferred Items – Brought forward to Task 9

| D1 Review Recommendation V-103 and update as necessary | Defer | see note 4 |
| --- | --- | --- |
| D2 Review Model Course V-103/1 and update as necessary | Defer | see note 4 |
| D3 Review Model Course V-103/2 and update as necessary | Defer | see note 4 |

Notes:

1.	Before reviewing IMO Resolution A. 857(20), Guidelines on VTS, it should be determined whether there is an urgent and compelling need for the Resolution to be revised.   If this is so, the reasons should be explained fully so that Administrations can prepare and submit proposals to the IMO Maritime Safety Committee for the item to be included on the work programme of the Sub-Committee on Safety of Navigation.  It should also be borne in mind when carrying out the review that this Resolution is “foot-noted” in Regulation 12 of the revised Chapter V of the SOLAS Convention.  The Committee noted that the VTS Manual revision schedule has been realigned by the Secretary General to correspond with VTS Symposiums.  Accordingly, the next edition of the manual will reflect major changes and will be completed for issue in 2008.

- This item has been transferred from the Operations Committee work proposals.  The Council may change this priority if the monitoring programme indicates that IALA needs to take some action on behalf of its Members.  Topics being monitored will not normally appear in the work targets for each session unless the Council approves specific action.

- The Council may change this priority if the monitoring programme indicates that IALA needs to take some action on behalf of its Members.  Topics being monitored will not normally appear in the work targets for each session unless the Council approves specific action.

- Recommendation V-103 and its model courses should not be changed until a number of Competent Authorities and VTS Training Institutes have gained experience with them and are therefore able to comment on the changes that may be necessary.  In addition, the Recommendation and model courses have recently been endorsed by IMO and it could be prejudicial to the interests of IALA for changes to be made to the documents too quickly.  In this regard, changes are not normally made to IMO documents at less than five-year intervals

- At VTS20 the Committee requested that Council provide clarification on the issue of World Wide Tracking prior to including it in the work programme.

Revised Work Plan

|  |  | Session 1 | Session 2 | Session 3 | Session 4 | Session 5 | Session 6 | Session 7 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | WG | VTS17 | VTS18 | VTS19 | VTS20 | VTS21 | VTS22 | VTS23 |
| Task 1 | Ops, Tech, PandT | X | X | X | X | X | X | X |
| Task 2 | Ops | X | X | X |  |  |  |  |
| Task 3 | Ops/ Tech | X | X | X |  | X | X |  |
| Task 4 | Ops |  |  | X | X | X |  |  |
| Task 5 | Ops, Tech | X | X | X |  | X | X | X |
| Task 6 | Tech |  | X | X | X | X | X |  |
| Task 7 | Tech | X | X | X | X | X | X |  |
| Task 8 | PandT | X | X | X | X | X | X |  |
| Task 9 | PandT |  | X | X | X |  |  |  |
| Task 10 | Ops | X |  | X | X | X |  |  |
| Task 11 | Ops, Tech, PandT | X | X | X | X | X | X |  |
| Tasks to be monitored |  |  |  |  |  |  |  |  |
| Task M1 | Monitor – Report by Rapporteur at each Session |  |  |  |  |  |  |  |
| Task M2 | Monitor – Report by Rapporteur at each Session |  |  |  |  |  |  |  |
| Task M3 | Monitor – Report by Rapporteur at each Session |  |  |  |  |  |  |  |
| Task M4 | Monitor – Report by Rapporteur at each Session |  |  |  |  |  |  |  |
| Items Deferred |  |  |  |  |  |  |  |  |
| Task D1 | Deferred – Pending the gaining of experience in the use of the Recommendation V-103 and model courses. |  |  |  |  |  |  |  |
| Task D2 |  |  |  |  |  |  |  |  |
| Task D3 |  |  |  |  |  |  |  |  |

Shaded Items have been amended during VTS21 / VTS22 Chairmans’ meeting.