REVISION OF THE IALA VTS MANUAL - WORK TARGETS FOR VTS 22

The following stages are due to be progressed or completed (VTS22 in bold):

| Item (Lead author) (1) | Initiate Draft (2) | Circulate to VTS Committee for comment and agreement (3) | VTS Committee to approve final draft (4) |
| --- | --- | --- | --- |
| Foreword (Ed) | # VTS22 | VTS23 | VTS24 |
| Preface (Ed) | VTS22 | VTS23 | VTS24 |
| Chapter 1 (Ed) Introduction Annex A: Definitions Annex B: Glossary of Abbreviations | Completed Completed Completed | Completed Completed Completed | ) Remains open for ) further additions ) arising from later ) chapters |
| Chapter 2 (Ed) Legal Framework | Completed | VTS21 (Working paper) VTS22 (Input Paper) | VTS22 (Output Paper) |
| Chapter 3 (Ed) Regulation of VTS | Completed | VTS21 (Working paper) VTS22 (Input Paper) | VTS22 (Output Paper) |
| Chapter 4 (WG1/2/3) Functions of VTS | Completed | VTS21 (Working paper) VTS22 (Input Paper) | VTS22 (Output Paper) |
| Chapter 5 (WG1/2/3) Types of VTS and Categories of Service | Completed | VTS22 (Working paper) | VTS23 (Output Paper) |
| Chapter 6 (WG1) Principles of Traffic Management | VTS22 | VTS23 (Input Paper) | VTS24 (Output Paper) |
| Chapter 7 (WG1 &2) Determining the need for a VTS | In progress | VTS22 (Working Paper) VTS 23 (Input paper) | VTS24 (Output paper) |
| Chapter 8 (WG1) Planning and Organisation | In progress | VTS22 (Working Paper) VTS 23 (Input paper) | VTS24 (output paper) |
| Chapter 10 (WG2) VTS Equipment | In progress | VTS22 (Working Paper) VTS 23 (Input paper) | VTS24 (Output paper) |
| Chapter 11 (WG3) VTS Personnel | In progress | VTS22 (Working Paper) VTS 23 (Input paper) | VTS23 (Output paper) |
| Chapter 12 (WG3) Qualification & Training | # VTS22 | VTS23 (Input paper) | VTS24 (Output Paper) |

Notes on Drafting – see over

Notes on Drafting

Where the work on a chapter is identified in column 2 as ‘Initiate draft’, it is suggested that some or all of the following processes be used as a means of producing the initial chapter format and to provide a framework for further work and comment:

- Identify topic headings (VTS21/6/1, Annex A) as an initial template.  Expand these as necessary to provide a framework for drafting.

- Identify existing relevant material contained in the VTS Manual 2002. This may, in some cases, be a more appropriate starting point, for example, with Chapter 11, VTS Personnel. (Note: An electronic copy of the Manual (2002) is available.)

- Identify and include any additional relevant topic headings.

- Identify and include any additional relevant material from other sources.

- Identify paragraphs/sections that need original drafting.  Nominate author(s)

- Liaise with other WGs, as necessary, to determine the need to incorporate other material.

- Produce the above as a single draft chapter document as an output paper for the VTS Committee.

## Format

The provisional format for chapter layout is that used for Chapter 1, (and the drafts of Chapters 2 & 3) which has been approved by the VTS Committee. The format may require some modification later; when Chapters 1 to 6 (Section 1) are completed a review will be undertaken to ascertain whether further change is needed.

### Illustrations

Illustrations are very important to enhance the utility of the manual and relevant diagrams and photographs should be included in the appropriate parts of the text.  Clearly these need to be of a very high quality.  Where these are available they should be positioned where required, where material is not immediately available space should be marked in the text by the use of an empty text box.   Requests for illustrations/photographic material should be passed to the editor, who may be able to put authors in contact with possible sources.