IALA Guideline

Gnnnn

Modernising Heritage Lighthouses: minimising negative impact

Edition x.x

Date (of approval by Council)

urn:mrn:iala:pub:gnnnn

Revisions to this document are to be noted in the table prior to the issue of a revised document.

| Date | Details | Approval |
| --- | --- | --- |

1.	Introduction	5

1.1.	Modernisation of heritage AtoN	5

1.2.	Responsibilities of the competent authority	5

2.	SCOPE	5

3.	Minimising impacts: Four phase process	6

3.1.	Phase 1. Understand impact of proposed modernisation work	6

3.2.	Phase 2. Adopt mitigation measures 	6

3.3.	Phase 3. Assess the need to conserve redundant equipment or fabric	8

3.4.	Phase 4. Keep record of modifications	8

4.	DEFINITIONS	8

5.	abbreviations	9

Annex a.	9

Annex b	9

List of Tables

Table 1	Example of table with row headers	5

Table 2	Example of table with column headers	5

List of Figures

Figure 1	Example of wrapping in line with text	4

Figure 2	Example of wrapped square	5

Figure 3	Example of how to achieve right justified equation number	7

# Introduction

Civilisations around the globe have utilised Aids to Navigation (AtoN) for centuries. This ancient service to the mariner has remained a constant requirement for all trade, travel and transport via sea, and is visible through the heritage lighthouses that remain in use on our coastlines.

This document is intended to provide AtoN managers with heritage management and conservation principles for consideration when modernising heritage lighthouses with essential AtoN equipment and/or or health and safety features.

## modernisation of heritage aton

Heritage lighthouses are AtoN with a level of significance due to their age, cultural associations, architectural style, rarity, and/or historic features. A large number of AtoN managers operate and maintain heritage lighthouses as part of their network.

Using heritage buildings for current day AtoN services means that modernisation of equipment is necessary to ensure the continued reliability of these critical lights. For the purposes of this guidance document, modernisation activities refer to:

- upgrades to existing AtoN equipment (lighting mechanism, power supplies)

- installation of new AtoN equipment (electrical cabling, antennas)

- modifications for health and safety (installation of handrails and safety grates, removal of hazardous materials)

- reinforcement of AtoN equipment for disaster resilience

Important considerations are recommended to ensure essential modernisation proposals are sympathetic to the heritage significance of historic lighthouses. While failure to do so may result in damage to or loss of a lighthouse’s heritage significance, this guidance document acknowledges budgetary constraints on conducting work that is sympathetic to heritage.

## Responsibilities of the competent authority

For the heritage management and conservation of lighthouses, it is the responsibility of the competent authority as a key stakeholder to define, create and provide the necessary instructions for workers carrying out the modernisation of cultural heritage sites. This task supports IALA Recommendation R1005.

# SCOPE

This guidance document is intended for use by Competent Authorities involved in heritage lighthouse management, which may include AtoN, port, aviation and other maritime authorities, aids to navigation providers, and contractors, developers and operators.

# Minimising impacts: four phase process for projects

When undertaking modernisation works, it is important to consider the impact that installing, altering or removing equipment may have on a heritage lighthouse.

The following Four Phase process for minimising impact can assist AtoN Managers reduce harm on a heritage building before, during and after the works.

Phase 1. Understand impact of proposed modernisation work

Phase 2. Adopt mitigation measures

Phase 3. Assess the need to conserve redundant equipment or fabric

Phase 4. Keep record of modifications

## Phase 1. Understand impact of proposed modernisation works

Identify significance of fabric that will be impacted in modernisation works. To do this, it is recommended research is conducted. Capture research findings within written statements – see Annex A)

Recommended principles to adopt:

### Conduct research prior to works

Prior to modernisation work taking place, research the history of the site and fabric by assessing historic photographs and archival documents.

Utilise non-invasive technology (e.g. LiDAR) to assess heritage structures and obtain data on surfaces, dimensions and contours.

### Engage with stakeholders and experts

Seek engagement with local communities, heritage management experts, historians, conservation architects and government-related agencies when planning work. Input from these bodies may assist modernisation works remain in line with the heritage value of the lighthouse.

### Consider a range of modification options

When modernisation work is considered, including a temporary modification, it is recommended a range of solutions be considered.

It is recommended the modification with the least amount of impact to heritage be considered as a preferred option.

### Change only as much as necessary

The least amount of change necessary should be implemented to ensure impact is restricted to essential modernisation works only.

## Phase 2. Adopt mitigation measures

Outline and undertake actions that minimise impacts to heritage fabric before, during and after the works.

Recommended principles to adopt:

### Avoid removal / demolition of heritage fabric

In the process of modernising a lighthouse, avoid the removal of heritage fabric where possible.

If removal of heritage fabric is required, consider exhibiting or keeping as a heritage artefact close to site (on display or in storage).

### Utilise existing penetrations in heritage fabric

When installing or adapting modern equipment, it is recommended drilling holes into heritage fabric is avoided and existing penetrations are used.

In the case new penetrations are essential for modernisation, it is recommended the least amount of holes are made to reduce impact on heritage fabric.

Figure 1. 	Corny Point Lighthouse – mounting of Sealite Star 2M remote monitoring unit inside lantern room

### Minimise visual impact of modern equipment on and inside heritage lighthouses

It is recommended modern installations and adaptions, such as electrical equipment and health and safety features, should seek to be visually discreet and unobtrusive.

Where redundant modern equipment is assessed to have no heritage or cultural significance (e.g. electrical cabling no longer used) it is recommended that it be removed from the lighthouse.

### Avoid irreversible modifications

When installing or adapting equipment and health and safety features within heritage lighthouses, it is recommended effort be made to ensure these features can be removed easily at a later date with minimal traces left behind.

### Avoid removal of heritage lighting systems as much as possible.

When considering changes to the AtoN lighting system, consider whether it is possible to keep existing heritage equipment in use (i.e. installing an LED inside a heritage lens).

### Avoid use of non-compatible equipment with existing heritage systems

Seek to install compatible equipment (e.g. LED Lighting, Solar Panel and other automatic mechanisms) alongside existing heritage systems for seamless integration. Implementation of this hybrid approach encourages the use of modern systems to support or back up heritage mechanisms without replacing them completely to ensure these systems are preserved.

### Utilise free-standing equipment that does not require fixing to structure.

When installing equipment inside heritage lighthouses, it is recommended that this equipment is installed in a way that avoids as much impact to the building. For example, rather than drilling a bracket into the lighthouse wall to fix equipment, find an alternative method which will not leave a permanent hole.

### Utilise Energy Efficient Equipment

When installing modern installation (e.g . LED Lantern/ Solar Panel) in a heritage lighthouse, it is recommended to use energy efficient equipment whenever possible in order to reduce carbon footprint and contribute to sustainability while ensuring the heritage lighthouse remains functional.

### Use expert craftspersons for projects

When modernising heritage lighthouses, it is recommended craftspersons with the appropriate skills and training be utilised in modernisation works.

It is recommended that craftspersons are made aware of the heritage significance of a lighthouse prior to commencing works.

## Phase 3. assess the need to conserve redundant equipment or fabric

Determine whether the item has heritage significance due to its age, rarity or association with influential figures or to a specific period in time. Determine what further action should be taken (remove, display as artefact, use in another lighthouse, etc.) Refer to G1080 for recommendations for artefact management.

Recommended principles to adopt:

### Assess equipment for heritage significance

Where redundant modern equipment is assessed to have no heritage or cultural significance (e.g. electrical cabling no longer used) it is recommended that it be removed from the lighthouse.

### Retain items of significance as artefacts

Where redundant equipment is assessed to have heritage or cultural significance, it is recommended to be retained as an artefact and utilised for display (refer to G1080).

## Phase 4. keep a record of modifications

Keep register of changes carried out (photographic and written records) – see Annex 2. Record decision-making made throughout works and retain these records for future use.

Recommended principles to adopt:

### Record decision-making throughout project

It is recommended all decisions made concerning a modification project be retained for future reference.

### Make records of modifications

It is recommended photographic and detailed written records of the modifications be taken before, during and after they are implemented. It is recommended these records be retained for future reference – see Annex B. Heritage Fabric Register.

# DEFINITIONS

The definitions of terms used in this Guideline can be found in the International Dictionary of Marine Aids to Navigation (IALA dictionary) at http://www.iala-aism.org/wiki/dictionary and were checked as correct at the time of publication. Where conflict arises, the IALA Dictionary should be considered as the authoritative source of definitions used in IALA documents.

| Term | Definition |
| --- | --- |
| Conservation | Measures and works undertaken to assist the retention of heritage significance. |
| Health and safety features | Equipment installed for the purpose of ensuring the safety of persons moving through and working inside lighthouse. |
| Heritage Fabric | All tangible parts of a heritage structure. |
| Heritage Lighthouses | Aids to Navigation with significant age, cultural associations, architectural style, rarity, and/or historic features. |
| Heritage Lighting Systems | Heritage lenses and all associated heritage equipment (e.g. mercury bath pedestals) |
| Modernisation | The process of installing or adapting modern AtoN services/technology and health and safety features. |

# abbreviations

This section should be typed with the Abbreviations style. The acronym or initialism is typed and then tab is pressed so that the style inserts the appropriate tabs and paragraph spacings e.g.:

NGO	Non-governmental organization

VTS	Vessel Traffic Services

The list should be typed in alphabetical order. The text automatically aligns as an indented paragraph until carriage return is hit and then the next term can be entered.

Example of pre-project heritage impact statement

Project detail

| Heritage Impact Statement for | - Cape Leeuwin Lightstation |
| --- | --- |
| Address and location description | - Leeuwin Road, Augusta WA 6290, Australia. Cape Leeuwin Lightstation is an intact historic precinct. - The proposed works impact the following parts of the precinct: - Lighthouse - Oil store |
| Location plan: | Example of Location plan |
| Prepared by: | - Australian Maritime Safety Authority |
| Date: | - 29/01/2020 |

Significance of place

Cape Leeuwin Lighthouse is recognised on Commonwealth, State and Local heritage registers.

- Commonwealth Heritage List: 105416

- Western Australian Heritage Register: 104

- Shire of Augusta River Heritage Register: 104

AMSA understands the potential for there to be additional heritage values and significance not identified in the below statements.

| Commonwealth Heritage List: | Statement of Significance Cape Leeuwin Lighthouse, completed in 1896, is important in illustrating the development of coastal navigation in Australia and the evolution of lighthouse design following the inter-colonial conference of 1873 in Sydney, which resulted in an agreed series of decisions which would result in a rough national chain of navigational aids. The lighthouse had two functions; to mark the coastal route to Perth via Albany and as the first landfall for vessels crossing the Indian Ocean to Australia. The upgrading of the lighthouse in 1925 under the Commonwealth illustrates the increasing importance of coastal shipping in Australia. Cape Leeuwin Lighthouse is exceptionally important in demonstrating in its original lens array and rotation mechanism the earliest use of the mercury bath system in Australia. In conjunction with the keepers cottages, the lighthouse is important in illustrating the principal characteristics of late nineteenth century lighthouse complexes in remote coastal areas. The lighthouse, situated on a narrow, sparsely vegetated strip of land and surrounded by sea on three sides, is significant as a prominent landmark feature on the coast of Western Australia (WA). The height of the lighthouse also makes it an outstanding landmark from the land and in particular from the approach road from Augusta. |
| --- | --- |
| Western Australian Heritage Register: | Aesthetic value - Importance as a striking feature within a barren and flat landscape. - The significance of the steep pitch cottage roofs and enclosed verandahs juxtaposed with the delicate spire of the lighthouse tower. Historic value - Importance as a link in the development of coastal lights around Australia. - Importance as an achievement by the Western Australian government as part of their active government building programme (1890s). - Importance as contributing to the local timber industry. - Importance of 1970s service buildings’ as demonstrating the development of lighthouse technology over the years. - Association with Sir John Forrest, M.C Davis, and George Temple Poole. - Importance as the first light in Australia to use a mercury bath pedestal mechanism, and as one of the last to convert from a pressurised kerosene mantel to an electrical halogen lamp. Scientific value - Importance in exhibiting and operating its original Chance Bros. lens and optical equipment. - Importance as an archaeological site as a whole. Social value - Importance as a popular tourist destination. - Importance as a heritage site recognised by Commonwealth, State, Local authorities. Rarity - Importance as demonstrating a way of life no longer practiced in current day. - Demonstrates the labour intensive jobs and isolated living conditions experienced by past keepers. Representativeness - Significance as an excellent example of a stone lighthouse tower. - Keepers’ quarters’ significance as an example of standard residences designed for public servants of the time. - Service buildings’ significance as examples of types of utilitarian buildings constructed during the 1950s and 1970s |

condition and use of place

| Current condition: | The lighthouse is the only building onsite which has retained its original function, and all buildings onsite display a high degree of authenticity. All structures are in relatively sound condition, however a number of structural issues have been identified – most notably flaking paint, moisture build-up and corrosion. Asbestos has also been detected in the oil store. |
| --- | --- |
| Current use of place: | The lighthouse is utilised as a marine Aid to Navigation – this is the original function of the tower. Tours for the general public are taken through the tower under a tourist licence. The Oil Store is utilised to house the power system for the AtoN. |

proposed activity

| Objective: | In recent years a number of issues have been identified that require rectification including: - Asbestos-cement sheeting present in Oil Store - Inverter failure - Poor power supply configuration - Corrosion to oil store door The objective of the project is to improve the condition of the building and it improve the AtoN’s electrical configuration. |
| --- | --- |
| Scope of works: | Recent assessment of the Lighthouse has identified the necessity of the following work: - Removal of all remaining asbestos material from Cape Leeuwin oil store. - Install alternative lining and blanking panel material. - Upgrade of electrical installation within oil store. • Replacement of severely corroded oil store door and reveal. The works seek to rectify the condition and structural integrity of the building. |
| Reasons for activity: | This work is deemed necessary as the removal of hazardous asbestos will enable AMSA to continue effective maintenance on the Lighthouse in a safer workplace for staff. Additionally, the replacement of the severely corroded oil store door will improve the Lighthouse’s overall condition and structural integrity. Upgrades to the tower’s electrical configuration is imperative to the continued operation of the site as an AtoN. |
| Options considered: | 1. Do nothing or delay works Advantages: - Minimise current financial year expenditure Impact: - Asbestos containing materials are not removed and remain a hazard to maintenance personnel and visitors to site. - Does not address safety concerns with the temporary inverter installation 2. Remove asbestos from Oil Store, delay electrical upgrades Advantages: - Removal of all known asbestos from these sites, thus improving safety for maintenance personnel and visitors. - Lower initial cost by delaying electrical upgrades. Impact: - Does not address safety concerns with the temporary inverter installation. - Existing electrical cables are installed within the wall cavities behind the existing asbestos lining, delaying the electrical upgrades and reinstating electrical equipment in a similar manner would result in additional works to make good the new wall linings when the electrical upgrade does occur. - Second stage of works required to undertake electrical upgrades. 3. Remove asbestos from inside the oil store. Undertaken electrical upgrades. Advantages: - Removal of all known asbestos from these sites, thus improving safety for maintenance personnel and visitors. - Eliminates safety concerns with the temporary inverter installation. - Makes Oil Store safe for tourist access in the future. Impact: - Higher initial cost but lower overall as undertaking the electrical upgrades in conjunction with the asbestos removal will eliminate the requirement to disturb or make good the new wall linings at a later date. - Repair of internal accessways The investigation and subsequent potential repairs are essential to: - Ensure the structural adequacy of the accessways and safety of personnel accessing the site - Reduce the potential for damage and cracking of the stonework due to corrosion of the embedded steel. |
| Impact of proposal: | Should the work be approved, Cape Leeuwin will be free of all known asbestos material, its electrical configuration will be rectified so to improve its AtoN capabilities. |

mitigation measures

Throughout the duration of the works, various precautions (listed below) will be put in place to ensure no impact is made to the Lighthouse’s heritage values.

General

- No work will infringe on the Keeper’s Cottages, sites of archaeological significance, or areas of environmental conservation.

- No fabric will be permanently removed from the structure aside from the following:

-	severely corroded fabric

-	asbestos cement sheeting

-	redundant, modern electrical/power supply features

- Removed fabric will be documented before, during and after removal.

- Fabric outlined in the scope for temporary removal during reparation and repainting will be returned to their existing position.

- Surface preparation techniques will be chosen based on their suitability, and small areas of fabric will be tested prior to use of the technique.

- Where possible, heritage fabric removed will be registered as an artefact in AMSA’s asset database and stored on-site.

- Daily reports will be generated and provided to AMSA.

- The work will be inspected at completion to ensure compliance with Burra Charter Guidelines.

- Work will adhere to the guidelines set out within AMSA’s Heritage Strategy.

- Any follow up works required will be scheduled ASAP.

- A Heritage Fabric Register will be completed following the work.

Repainting

- Surfaces will be painted in accordance with the AMSA Lighthouse Coating Specification.

- No new colour schemes will be implemented during repainting.

- Any replacement materials will be painted to match existing colour scheme.

Corrosion reparations

- All corroded fabric outlined in the scope will be repaired to replicate the original design.

- Wherever possible, fabric will be repaired rather than replaced.

- Replacement materials will be fabricated to respect the original design of the lighthouse, and will be painted to match the existing colour scheme.

Electrical installations/removals/reparations

- Upgrades to the electrical configuration will seek to minimise visual impact inside the lighthouse.

- Existing penetrations in the fabric will be utilised.

- In the instance new penetrations are required, they will be limited in number, and installed in suitable areas (such as stonework mortar) so as to limit impact on heritage fabric)

Asbestos removal

- Asbestos cement sheeting panels will be removed and disposed of in a safe manner that does not impact on surrounding environment.

| Positive Impacts: | • Improved condition of Oil Store and Lighthouse • Improve safety of contractors and general public accessing the place • Improve original use/function of Lighthouse as a marine AtoN • Lessen impact of modern electrical set-up on aesthetics |
| --- | --- |
| Negative Impacts: | • Loss of some heritage fabric |
| Assessment of impacts: | AMSA determines that none of the heritage values of Cape Leeuwin Lighthouse will be impacted as the project seeks to retain these values identified above. The steel sheeted door and steel frame (jamb) previously replaced lining board doors and are not original. The door opening however is original and will not be altered during installation of the new door and jamb. The Oil Store panels identified as containing asbestos were installed during later renovations of the tower and are not original. Electrical cabling and related works will not infringe on heritage fabric. |

Summary

The objectives of the work proposed at Cape Leeuwin Lightstation are to rectify known hazards in the oil store, improve electrical configuration of the AtoN and improve the condition of the building. Failure to rectify issues may result in future, invasive project works which may have a major impact on heritage values. Failure to rectify issues will also inhibit AMSA’s statutory duty to maintain critical AtoN for mariners at sea.

AMSA has determined that the works proposed do not threaten the place’s heritage values, and that the mitigation measures in place will reduce the risk of impacts to the place’s heritage values.

Example of Hertige fabric register

Example of the heritage fabric regicter card

| Name: | Aids to Navigation (AtoN) AN350 Cape Leeuwin |
| --- | --- |
| Date of change: | 21 June 2017 |
| Lighthouse feature: e.g. Balcony balustrade, internal catwalk, tower stairs, etc. | Light source / optic |
| Original fabric: | Existing lampchanger |
| Replacement materials/materials added: | LED beacon |
| Description of alterations made: e.g. removal process, etc. | The existing lamps, lampchanger and control switchboard were removed and a new switchboard installed in the original switchboard position. The LED array was installed and focussed inside the lens. The lantern control switchboard was removed and replaced with an electrical distribution board with the LED controller mounted in the same enclosure. The PE cell and rotation detection were replaced and wired back to the LED controller. This controller has GSM remote monitoring. |
| Before photo: | After photo: |
| Contractors responsible: | Australian Maritime Systems Group (AMSG) |