# IALA VTS MANUAL

REVISED MANUAL STRUCTURE, REVISED WORK PLAN AND WORK TARGETS FOR VTS 24

##### Structure of the Manual

During the Drafting Session in March 2006 it was decided to make some small changes to the structure.  Emergency and Operational VTS Procedures, formerly separate chapters, were combined into a single chapter.  Some chapter titles were modified to reflect more fully their purpose and content, and the order of Chapters in Section 3 was re-arranged.   The revised structure is at Annex C.

##### Work Plan and Work Targets for VTS 24

An updated Work Plan (Annex A) is attached and takes into account the considerable work achieved at the Drafting Session.

The Work Targets for VTS 24 (Annex B) show that nine chapters (Chapters 4 – 12 inc) are in final draft; Working Groups will be asked to agree the content of these chapters and give approval for the draft chapters to go forward.

Drafting work on the  remaining four chapters is planned for the session.

IALA Website – VTS Manual

The VTS part of the website provides an area for the VTS Manual and includes final drafts of the chapters 4-12.  Also included is a ‘comments’ section for delegates to forward, in advance of VTS 24, any proposals for change to the drafts.   This would greatly speed up the staffing process and any comments would be welcomed.

Annex A:  IALA VTS Manual - Revised Work Plan - July 2006

Annex B:  Work Targets For VTS 24

Annex C:  IALA VTS Manual - Chapter Structure For 2008 Edition

# Annex A:  IALA VTS MANUAL - REVISED WORK PLAN – JULY 2006

| Sect | Chapter No. | Title | Author | Initiate Drafting | Draft for Circulation to VTS Committee | Final version to for agreement | Drafting Status | Approval Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  | Foreword | Editor | VTS 22 | VTS 24 | VTS 25 |  |  |
|  |  | Preface | Editor | VTS 22 | VTS 24 | VTS 25 |  |  |
|  | 1 | Introduction | Editor | VTS 20 | VTS 21 | VTS 21 | Completed | Completed |
|  | 2 | Legal Framework | Editor | VTS 21 | VTS 21 | VTS 22 | Completed | Completed |
|  | 3 | Regulation of VTS | Editor | VTS 21 | VTS21 | VTS 22 | Completed | Completed |
|  | 4 | Objectives of VTS | WG1(+ 2/3) | VTS 20 | VTS 21 | VTS 22 | Completed | VTS 24 |
|  | 5 | Types and Functions of Traffic Services | WG1 (+2/3) | VTS 21 | VTS 22 | VTS 23 | Completed | VTS 24 |
|  | 6 | Principles of Traffic Management | WG1 | VTS 22 | VTS 23 | DS | Completed | VTS 24 |
| 2 | 7 | Determining the need for a VTS | WG1 & 2 | VTS 20 | VTS 22 | VTS 23 | Completed | VTS 24 |
|  | 8 | Planning and Organisation | WG 1 | VTS 20 | VTS 22 | DS | Completed | VTS 24 |
|  | 9 | Procurement Considerations | WG2 | VTS 22 | VTS 23 | DS | Completed | VTS 24 |
|  | 10 | VTS Equipment | WG2 | VTS 20 | VTS 23 | DS | Completed | VTS 24 |
|  | 11 | VTS Personnel | WG3 | VTS 21 | VTS 22 | VTS 23 | Completed | VTS 24 |
|  | 12 | Training and Qualification | WG3 | VTS 22 | VTS 23 | DS | Completed | VTS 24 |
| 3 | 13 | Promulgation of VTS Information | Editor | VTS 22 | VTS 22 | VTS 23 | Completed | Completed |
|  | 14 | Administrative Requirements | WG ops | VTS 24 | VTS 25 |  |  | VTS 25 |
|  | 15 | Archives and Records | WG Inf Mngnt | VTS 24 | VTS 25 |  |  | VTS 25 |
|  | 16 | Public Information | WG P & Training | VTS 23 | DS | VTS24 |  | VTS 25 |
|  | 17 | VTS Operational Procedures | WG Ops | DS | VTS 24 | VTS 24 | Initial Draft | VTS 24 |

VTS 24	 - Sep 2006		VTS 25	 - Mar 2007		VTS 26	- Sep 2007

Annex B:   WORK TARGETS FOR VTS 24

The following stages are due to be progressed or completed (VTS 24 in bold):

| Item (Lead author) (1) | Initiate Draft (2) | Circulate to VTS Committee for comment and agreement (3) | VTS Committee to approve final draft (4) |
| --- | --- | --- | --- |
| Foreword (Ed) | # VTS22 | # VTS24 | ## VTS25 |
| Preface (Ed) | VTS22 | VTS24 | ## VTS25 |
| Chapter 1 (Ed) Introduction Annex A: Definitions Annex B: Glossary of Abbreviations | Completed Completed Completed | Completed Completed Completed | Completed ) Remains open for ) further additions ) arising from later ) chapters |
| Chapter 2 (Ed) Legal Framework | Completed | Completed | Completed |
| Chapter 3 (Ed) Regulation of VTS | Completed | Completed | Completed |
| Chapter 4 (WG1/2/3) Functions of VTS | Completed | Completed | VTS24 (Output Paper) |
| Chapter 5 (WG1/2/3) Types and Functions of Traffic Services | Completed | Completed | VTS24 (Output Paper) |
| Chapter 6 (WG1) Principles of Traffic Management | Completed | VTS23 (Input Paper) | VTS24 (Output Paper) |
| Chapter 7 (WG1 &2) Determining the need for a VTS | Completed | Completed | VTS24 (Output Paper) |
| Chapter 8 (WG1) Planning and Organisation | Completed | Completed | VTS24 (Output Paper) |
| Chapter 9 (WG2) Procurement Considerations | Completed | VTS23 (Input paper) | VTS24 (Output Paper) |
| Chapter 10 (WG2) VTS Equipment | Completed | VTS23 (input paper) | VTS24 (Output Paper) |
| Chapter 11 (WG3) VTS Personnel | Completed | Completed | VTS24 (Output Paper) |
| Chapter 12 (WG3) Training & Qualification | # Completed | VTS23 (Input paper) | VTS24 (Output Paper) |
| Chapter 13 (Ed) Promulgation of VTS Information | Completed | Completed | Completed |
| Chapter 14 (WG 3 (+2)) Administrative Requirements | # VTS 24 | ### VTS 25 | VTS25 |
| Chapter 15 (WG2 +1/3) Archives and Records | # VTS 24 | ### VTS25 | VTS 25 |
| Chapter 16 (WG3) Public Information | #### VTS 23 | ## DS Mar 2006 | ## VTS24 (Output Paper) |
| Chapter 17 (WG1) VTS Operational Procedures | #### DS | ## VTS24 | ## VTS24 (Output Paper) |

VTS 24	 			Sep 2006

VTS 25	 			Mar 2007

VTS 26				Sep 2007

Annex C:  IALA VTS MANUAL - CHAPTER STRUCTURE FOR 2008 EDITION

SECTION 1:	VTS - REGULATORY FRAMEWORK AND FUNCTIONS

Chapter 1 		Introduction

# Purpose of the Manual

IALA Publications

Organisation and Consultative Bodies concerned with VTS

Development of VTS - A Brief History

Annex A:   Definitions

Annex B:    Glossary of Abbreviations

Chapter 2		Legal Framework

International Law

IMO Conventions, Resolutions and Guidelines

National Law

`		Harbour/Port Byelaws and Regulations

Authority

Liability

Environmental Law

Chapter 3		Regulation of Vessel Traffic Services

IMO resolution Guidelines for VTS

IALA

Other regimes - EU

National

The need for common approach to standards

Chapter 4 		Objectives of VTS

Safety of Maritime Traffic

Safety of Life

Risk Reduction

Risk Management

Protection of the Marine Infrastructure

Efficient Vessel Traffic Flow

Efficient management of Port marine resources

Protection of the Environment

Security in the Maritime Domain - Its impact on VTS

VTS in an inter-modal transport system

Search and Rescue

Chapter 5		Types and Functions of Traffic Services

Types of VTS:

Harbour and harbour approaches

Places of  Refuge (ports) – implications for VTS

Coastal waters and International Straits

Waterways governed by Treaty

Waterways not governed by Treaty

Places of Refuge (non port) – implications for VTS

Offshore

Legal status

Inland Waterways

Categories of Service:

Information Service

Navigational Assistance Service

Traffic Organisation Service

Allied Services

Chapter 6		Principles of Traffic Management

Development of safe standard operating procedures

Principles of safe waterspace and traffic management

Two-way and one-way traffic occupancy; channel width, length, points-of-no-return, ship size and manœuvrability.

High-risk ships and cargoes

Risk induced by geography and hydrography

Other factors that can increase risk.

Allocation of waterspace. Slot management

Authorisation of ship movements, allocation of priority

Provision of navigation assistance

Traffic organisation service

Shore based Pilotage

SECTION 2		ESTABLISHING AND STAFFING A VTS

Chapter 7		Determining the Need for a VTS

Needs Analysis, including those of allied services

Hazard Identification

Risk assessment

Risk Control Options

Service provision

Cost/benefit Analysis

International Regulations

Chapter 8 		Planning and Organisation of VTS

Geography/Hydrography

Area limits, boundaries, Sectors, Coverage

Positional and Navigational Accuracy requirements.  Chart Accuracy.

Services

Service provision: mandatory/voluntary

Categories provided

Allied Services, including SAR

Management

Prohibited or Dangerous areas, safety zones (place of safety), anchorages

Traffic management, TSS, Separation Criteria

Pollution Control

Surveillance and Monitoring

VTS Personnel

Pilot/VTS interface.  The role of Pilots in a VTS

Legal  Basis

Constitution

Enforcement, Control, Direction (definitions/Difference)

Infringement of Regulations.

Contributory and Participatory Navigation Assistance

Advice and Information Services

Accident avoidance.

Chapter 9 		Procurement Considerations

Procurement Process:

Requirements capture

Feasibility studies and project definition

Options

Development, manufacture, installation and acceptance.

Demonstrators and modelling.

Project Management:

Management plan

Quality

Project risk plan

Scheduling

Acceptance testing

International Standards

Human factors

Chapter 10		VTS - Equipment

Introduction

Performance Requirements

Non-functional Requirements

Sensors

Radars

AIS/Transponders

Communications DF

Optical, TI, LL devices

Meteorological data

Tide, Tidal & Wave  Data

Communications

Voice HF/UHF/VHF/SHF

Data

EDI/e-mail

Telephone/Fax/Telex

Traffic Lights

Processing

Data Displays; Symbology

Correlation/ Fusion

Sensor Co-ordination 	Track combining

Track Table

Traffic Image

Tidal stream model and display

Depth of water/ height of tide model

Dynamic safe-depth (UKC) model

Alarms

Presentation

Displays, HMI, Symbology, Audio

Pilot aids - carryaboard equipment

Information Management

Database management systems

Standards, Accuracy, Quality.

Work Environment

Air supply

Lighting

Workstations

Equipment spaces

Fire/lightning protection

EMC

Security

Chapter 11 		VTS Personnel

Key personnel - ashore and afloat

The Ships Captain

Pilot

VTS

Captain/Pilot/VTS relationship

VTS Manager

VTS Superviser/Watch leader

VTS Operator

VTS Centre - watch organisation

Functions, duties & tasks

Delegated responsibilities.

Chapter 12		Training and Qualifications Required for VTS Personnel

International Framework - STCW

Recruitment, Training and Certification

Model Courses

Refresher training and validation.

SECTION 3  		CONDUCT AND MANAGEMENT OF VTS OPERATIONS

Chapter 13		 Promulgation of VTS Information

This chapter provides a template from which VTS authorities could construct their own data sheets of information needed in the VTS centre and made available on the web and in appropriate nautical publications.  Methods of Promulgation.

Chapter 14		Administrative Requirements for Operating a VTS

Co-ordination and planning of local resources.

Liaison with allied services

Agents

Customs

Security agencies

Quarantine

Auto-billing

PEC

Chapter 15		Archives and Records

Required to assist:

Re-construction of marine incidents

Litigation

Administration (Chapter 14)

Shipping , masters, pec data.

Chapter 16		Public Information

Public awareness, development of public image of VTS

Routine dealings with press and media.

Procedures for handling media following accidents and emergencies.

Chapter 17		VTS Operational Procedures

Data acquisition, reports, reporting points.

Identification.

Development of Traffic image

Traffic organisation and management.

Monitoring and authorising traffic movements

Passage Plans; exchange electronically

Detection of unsafe/unauthorised operations:

Infringements of exclusion zones

Infringements of separation intervals

Provision of support services

Relationships with Pilots and Ship's Masters