| Schedule 2010/2011 for the Correspondence Group (CG) on implementation of IMO e-navigation strategy |  |  |
| --- | --- | --- |
| WHAT? | WHO? | DEADLINE |
| NAV 56. IMO/HQ |  | July 26-30 |
| Invitation to CG for inputs on GAP analysis. | Chairman | August 30. |
| Draft document to CG on questions to STW 42 | Chairman | September 13 |
| Inputs to chairman on GAP | Members | October 15 |
| Inputs to chairman on questions to STW 42 | Members | October 22 |
| Collection of inputs on GAP for comments to CG | Chairman | October 29 |
| Work shop on data structure | Members | November 4-5 |
| Paper submitted to IMO for STW 42 | Chairman | November 5 |
| Comments on collated inputs on GAP to chairman | Members | November 19 |
| Paper submitted to IMO for COMSAR 15 | Chairman | December 17 |
| STW 42. IMO/HQ |  | January 24-28. |
| First draft report for NAV57 to CG | Chairman | February 26 |
| COMSAR 15. IMO/HQ |  | March 7-11. |
| Second draft report for NAV 57 with additions from COMSAR to CG | Chairman | March 14. |
| Inputs to chairman on NAV 57 draft report | Members | March 24. |
| Paper submitted to IMO for NAV 57. | Chairman | April 1. |
| NAV 57. IMO/HQ |  | June 6-10. |

Rev.30/8-2010