## Slide 1: Report on IALA’s contribution to EfficienSea 2
Nick Ward, IALA Project Manager for EfficiernSea 3 April 2017
THIS PROJECT HAS RECEIVED FUNDING FROM THE EUROPEAN UNION’S HORIZON 2020 RESEARCH AND INNOVATION PROGRAMME UNDER GRANT AGREEMENT NO. 636329

## Slide 2: About EfficienSea 2
EU H2020 funded €11m
DMA led, 32 partners - incl. IALA
to enhance safety of navigation and increase efficiency at sea
e-navigation services
Maritime Cloud
Comms incl. VDES

## Slide 3: Status report
IALA leads Task 1.2 (Project/Test Bed Liaison) with CIRM, DMA & OFFIS
IALA leads Task 1.3 (Standardization) with CIRM and UKHO.
IALA also contributes to WP 2 (Communications - VDES) and WP 3 (Maritime Cloud).
Core work in Tasks 1.2 and 1.3 completed. Deliverables D1.4 and D1.5 accepted. Information on websites
Completed Work Plan for the second year of the Project, progressing work on VDES and Maritime Cloud
Work Plan for the third year is now being carried out.

## Slide 4: Way of working
Consultants developing documentation for VDES and the Maritime Cloud
Technical development of VDES channel model
Close cooperation with IALA ENAV WGs
Documents produced as E2 deliverables
Will become IALA recommendations/guidelines
Providing continuity beyond the E2 project.

## Slide 5: Informing stakeholders
Information plan on VDES
- important in the lead up to WRC 2019
2. Information plan to raise awareness of Maritime Cloud
- especially for IMO MSC
3. Coordinated with overall E2 Communications Strategy
4. IALA website
- test bed information updated
- information for new standards pages
- links to other websites (IMO, ITU, IHO, E2)

## Slide 6: Maritime Cloud Workshop proposal, Nov 2017
Workshop will focus on implementation:
  Purpose, user needs
  Business model
  Governance options
  Technical standards
International seminar to encourage adoption of MC, demonstrations (March 2018?)

## Slide 7
Deliverables for 2017-18
Deliverable | Description | Input to ENAV
Draft D 1.10 | Strategy for Future Digital Communications | ENAV 20
Draft D 1.11 | Report on Future Digital Communications | ENAV 20
Draft D 1.12 | Structure of IALA Documentation on AIS & VDES | ENAV 20
Draft D 1.13 | Technical Overview of VDES | ENAV 20 & 21
Draft D 1.14 | Draft IEC Specification for VDES | ENAV 20
Draft D 1.15 | Draft text on VDES for IALA Navguide | ENAV 20
Draft D 1.16 | Implementation, Validation and Demonstration of VDES Compatibility Test Bed | ENAV 21
Draft D 1.17 | Review of VDES Test Results, New Test Plan and Revised Channel Model | ENAV20 & 21
Draft D 1.18 | Updated website content on Standards and Test Beds | ENAV 20 & 21
Draft D 1.19 | Presentation on Maritime Cloud | ENAV 21
Draft D 1.20 | Standardization Plan for Maritime Cloud | Post ENAV 21
Draft D 1.21 | Report of IALA Workshop on Maritime Cloud | Post ENAV 21
Draft D 1.22 | Information Plan for VDES | ENAV 20
Draft D 1.23 | Presentation on VDES | ENAV 20

## Slide 8: For more information, contact nick.ward@iala-aism.org
THIS PROJECT HAS RECEIVED FUNDING FROM THE EUROPEAN UNION’S HORIZON 2020 RESEARCH AND INNOVATION PROGRAMME UNDER GRANT AGREEMENT NO. 636329