VTS46-5.1.5 Work programme for completing the revision of resolution A.857(20)

**Work programme for completing the revision of resolution A.857(20)**

| **Task** | **2018** | | | | **2019** | | | | | | | |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **IM[[1]](#footnote-1)**  **(10-13 Apr 2018)** | **ICG[[2]](#footnote-2)** | **VTS45**  **(1-5 Oct 2018)** | **ICG** | **NCSR 6**  **(16-25 Jan)** | **VTS46**  **(25 Feb – 1 Mar 2019)** | **ICG** | **MSC101**  **(5-14 Jun 2019)** | **Seminar**  **(24-28 Jun 2019)** | **ICG** | **VTS47**  **(23-27 Sep 2019)** | **NCSR 7**  **(Jan/Feb 2020)** |
| IALA intersessional meeting to establishing a common understanding of the submission and the tasks required | X |  |  |  |  |  |  |  |  |  |  |  |
| Draft skeleton for revised/new Resolution |  | X | X |  |  |  |  |  |  |  |  |  |
| Draft Work Plan |  | X | X |  |  |  |  |  |  |  |  |  |
| Prepare proposal for a Workshop on the revision of A.857(20) for Council approval |  | X | X |  |  |  |  |  |  |  |  |  |
| **First draft** of revised/new Resolution |  |  | X |  |  |  |  |  |  |  |  |  |
| Information Paper/s to NCSR and MSC[[3]](#footnote-3)   * Status of the revision * Invitation to the workshop |  |  | X | X | X |  |  | X |  |  |  |  |
| **Second draft** of revised/new Resolution |  |  |  | X |  | X |  |  |  |  |  |  |
| **Workshop** with stakeholders to review the draft revision |  |  |  |  |  |  |  |  | X |  |  |  |
| **Final draft** of revised/new Resolution |  |  |  |  |  |  | X |  |  | X | X |  |
| Review by NCSR of final revised/new Resolution for approval by the Committee and subsequent adoption by the Assembly |  |  |  |  |  |  |  |  |  |  |  | X |

1. IALA Intersessional Meeting of Working Group 1 of the VTS Committee [↑](#footnote-ref-1)
2. IALA Correspondence Group (ICG) for the revision of A.857(20) [↑](#footnote-ref-2)
3. Note submission end dates and need for Council approval:

   NCSR6 - submission deadline is 16 Oct. 2018

   MSC101 - submission deadline is 5 Mar (bulky), 2 Apr (INF-doc 1-6 pages) 2019

   NCSR7 - submission deadline will be 15 Oct 2019 [↑](#footnote-ref-3)