**ARM COMMITTEE 2014-18 WORK PROGRAMME**

**Status Report (ARM4)**

**Overall Status:**

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Task** | **Start Session** | **Planned End Session** | **Revised End Session** | **Progress Indicator** | | | | **Status Overview** |
| **Green** | **Yellow** | | **Red** |  |
| **TD#1 – Requirements for AtoN systems** |  |  |  |  |  |  | |  |
| 1.1.1 Contribute to standards generated by Secretariat | 4 | 7 |  |  |  |  | |  |
| 1.1.2 Workshop on AIS AtoN (real and virtual) | 2 | 4 | 5 |  |  |  | | Initiated ARM2 |
| 1.1.3 Guideline on the marking of wrecks as defined by the Nairobi Wreck Convention | 4 | 7 |  |  |  |  | |  |
| 1.1.4 Guideline on the use of pictograms on AtoN | 3 | 5 | 7 |  |  |  | | Commenced ARM3 |
| 1.1.5 |  |  |  |  |  |  | | Task merged with 1.1.4 ARM3 |
| 1.1.6 Guideline on the use of mobile AtoN | 4 | 7 |  |  |  |  | |  |
| 1.2.1 Populate S-100 as requested by ENAV Committee | 1 | 7 |  |  |  |  | | Commenced ARM1 |
| **TD#2 – Management for AtoN services** |  |  |  |  |  |  | |  |
| 2.1.1 Develop guidance for AtoN authorities on disaster recovery | 1 | 4 | 5 |  |  |  | | Commenced ARM1 |
| 2.1.2 Contribute to standards generated by Secretariat | 4 | 7 |  |  |  |  | |  |
| 2.1.3 Consider guidance for authorities on the use of enavigation services | 4 | 7 |  |  |  |  | |  |
| 2.5.1 Develop guidance on the management of AtoN in environmentally protected areas | 2 | 7 |  |  |  |  | | Commenced ARM2 |
| **TD#3 – Marine Spatial Planning** |  |  |  |  |  |  | |  |
| 3.1.1 Develop guidance for AtoN authorities on the use of Marine Spatial Planning | 1 | 4 | 5 |  |  |  | | Commenced ARM1 |
| 3.4.1 Oversee development of Risk Management Toolbox | 4 | 7 |  |  |  |  | | New task ARM4 WG3 |
| 3.4.2 Develop guidance on PAWSA | 4 | 7 |  |  |  |  | | New task ARM4 WG3 |
| 3.4.3 Develop guidance on SQUART | 4 | 7 |  |  |  |  | | New task ARM4 WG3 |
| 3.4.4 Develop guidance on use of IWRAP | 5 | 7 |  |  |  |  | | New task ARM4 WG3 |
| 3.4.5 Training / workshop / seminar in association with WWA | 5 | 7 |  |  |  |  | | New task ARM4 WG3 |
| 3.4.6 IALANET | 5 | 7 |  |  |  |  | | New task ARM4 WG3 |
| **TD#4 –** **International coordination and liaison** |  |  |  |  |  |  | |  |
| 4.1.1 |  |  |  |  |  |  | | Task cancelled ARM3 |
| 4.2.1 |  |  |  |  |  |  | | Task cancelled ARM3 |
| 4.2.2 Coordinate a limited review of the IALA Navguide to incorporate amended guidelines and recommendations and other necessary updates via wiki | 1 | 7 |  |  |  |  | | Commenced ARM1 |
| 4.2.3 |  |  |  |  |  |  | | Task cancelled ARM3 |
| 4.2.4 |  |  |  |  |  |  | | Task cancelled ARM3 |
| 4.2.5 Amend IALA dictionary as appropriate including harmonisation of definition of AtoN | 1 | 7 |  |  |  |  | | Commenced ARM1 |
| 4.2.6 Map existing ARM documentation to 7 overarching standards | 3 | 7 |  |  |  |  | | New task ARM3  Commenced ARM3 |
| 4.2.7 Rewrite ARM documentation to meet new document structure in conjunction with IALA assistance | 3 | 7 |  |  |  |  | | New task ARM3  Commenced ARM3 |