| VTS Committee Work Programme |  |  |  |
| --- | --- | --- | --- |
| Standard | S1040 Vessel Traffic Services |  |  |
| Topic Area | VTS Operations / Auditing and Assessing |  |  |
| Task | Develop guidance on demonstrating VTS performance, effectiveness and contribution |  |  |
| Objectives of the task | To help competent authorities and VTS providers set clear and assessable performance expectations and measurable operational objectives, select suitable indicators and evidence, and demonstrate that VTS is operating as intended and contributing to safety, efficiency and environmental protection. |  |  |
| Expected outcome | A new and/or revised IALA Guideline providing a common framework for demonstrating VTS conformity, performance, effectiveness and contribution. The outcome may also identify minimum measurement areas and, where justified, a limited set of core indicators, and provide guidance on setting locally appropriate targets, thresholds or performance bands. |  |  |
| Compelling need | IMO Resolution A.1158(32) requires VTS providers to set operational objectives and regularly evaluate whether they are being achieved. Existing IALA guidance already addresses important parts of VTS performance assurance, including objectives, management, auditing, technical performance and incident reporting. The principal gap is the absence of a common framework connecting requirements, objectives, indicators, evidence, reporting and assessment. Recent IALA events have also identified a need to demonstrate the safety benefits and wider positive effects of VTS. A case study on Nordic VTS indicator frameworks shows that similar areas are measured using different terminology, classifications, calculation methods, targets and reporting practices. Common concepts, definitions, measurement principles and calculation rules would improve consistency and comparability, while numerical values would normally be determined by the competent authority based on local risks, operational requirements and the purpose of the VTS. |  |  |
| Strategic Alignment | G1 – Marine Aids to Navigation are developed and harmonised through international cooperation and the provision of standards. S1 - Develop standards suitable for direct citation by States, in areas deemed important by the General Assembly, and the related Recommendations and Guidelines. S3 - Coordinate the further development of Marine Aids to Navigation, taking into account evolving operational and functional requirements, new techniques, new technologies and sustainability. S6 - Improve and harmonise the delivery of VTS globally and in a manner consistent with international conventions, national legislation and public expectations, to ensure the safety and efficiency of vessel traffic and to protect the environment. |  |  |
| Scope | In Scope: - roles of competent authorities and VTS providers; - regulatory and authorization requirements, operational objectives and performance expectations; - common terminology and interpretation for VTS performance assurance; - common minimum measurement areas and, where justified, a limited set of core indicators; - principles for defining indicators and other performance evidence, including quantitative and qualitative evidence; - guidance for setting locally appropriate targets, thresholds or performance bands and interpreting results; - reporting, review, audit, assessment and continuous improvement; - demonstrating VTS effectiveness and contribution without attributing safety, efficiency or environmental outcomes solely to VTS Out of scope: - universal mandatory numerical targets; - replace technical performance requirements in the G1111 series; - define performance targets for individual VTS personnel; or |  |  |
| Brief and concise description of the work to be undertaken and programme milestones | Review existing IALA guidance and current practices, identify gaps or overlaps and develop the most suitable guidance. Develop a common framework linking regulatory and authorization requirements, operational objectives, service-level expectations, indicators, evidence, reporting and assessment. Consider minimum measurement areas and, where justified, a limited set of core indicators, together with guidance for setting locally appropriate targets, thresholds or performance bands. Determine whether the outcome should be a new Guideline, revisions to existing Guidelines, or a coordinated combination of both. Key milestones include: - Session 1 - Confirm scope, review documents and identify gaps. - Session 2 - Agree the framework, terminology and measurement approach - Session 3 - Prepare and review the first draft. - Session 4 - Complete the draft for approval. Session 5 - Finalise the document, if required. |  |  |
| Expected numbers of sessions for completion | Session number:5 62 63 64 65 66 |  |  |
| Committee notes | Origins |  |  |
|  | Agreed by session | TD# | Comments |
|  | Approved by Council | (Council Session) | (Date) |
|  | Revision Notes: |  |  |