IALA - LIST OF MAIN ACTIVITIES

# AND

# ASSOCIATED RISKS

| No | ACTIVITY | PROBABILITY | IMPACT or CONSEQUENCE for IALA (High / Low) | TYPE OF RISK (Finance, reputation, etc.) | EXISTING MITIGATORS | RESIDUAL RISK / (PROBALITY / IMPACT) | ACTION |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Produce guidance documents for IALA membership. - Recommendation – highest level of document. ‘What you should do’. - Guidelines – ’how to do it’ - Manuals – touches on a large topic (e.g. VTS) All guidance is not mandatory, but ‘international best practice’ | Low | High | Reputation | Risk factor – IMO endorsement may reduce IALA’s risk. IALA process for creating and approving documents | Low | QA system for IALA HQ |
| 2 | Provision of information - IALA Bulletin (periodical) for information of IALA membership | Low | Low | Reputation | In house editorial meeting to scrutinise material Experienced editor | Low | Secretariat to consider general disclaimers |
|  | - Website & Dictionary | Low | High | Reputation | Disclaimers Quality assurance Reports from members | Low | Application of quality management Advice from French lawyer |
| 3 | - Organise workshops, seminars, symposiums and conferences. These often result in output conclusions and recommendations. - Physical risk / personal safety of those attending – who is liable? - Following recommendations and making investment / operational decisions etc | 1 Low 2 Low 3 Low | 1 High 2 High 3 High | Reputation Liability Reputation Liability | 1 Review by Secretariat and scrutiny by Council 2 Insurance for workshops on-site and outside 3 See 1 above | 1 Low 2 Low 3 Low | Place list of items (including insurance) to be taken into account and place in IALA guidance document on organising a workshop |
| 4 | Advice offered by IALA experts in responses to administrations; - Advise on interpretation of int’l rules and regulations - Advise on solutions | 1 Low 2 High | 1 High 2 High | Reputation Liability Reputation Liability | 1 Careful selection of experts (and internal scrutiny of mission report within IALA) | 1 Low 2 High | - Explore suitable Insurance cover - Develop proforma agreement - Contract to state that French Law applies ** - State conditions and terms in e-mails |
|  | - Advise on training | 3. Low | 3. Low | Reputation |  | 3. Low |  |
| 5 | Advice offered by private consultants engaged by IALA - Adv on int’l rules - Adv on solutions | 1 Low 2 High | 1 High 2 High | ? ? | 1 Don’t take ‘unknown’ consultants | 1 Low 2 High | Develop proforma contract including requiring professional indemnity insurance |
| 6 | Product certification process | Low | Low | N/A | High level of expertise in Committee drafting the templates | Low | Certification process abandoned |
| 7 | Internal operational risks: - Infringing on intellectual property rights of others (copying documents, pictures) - Correspondence | 1 High 2 Low | 1 Low 2 Low | Liability Reputation | 1 None! 2 None! | 1 Low 2 Low | 1 Awareness among staff 2 Develop disclaimer |
|  | - Domestic mishaps - Non-contractual wrongs (torts?) | 3. Low 4 Low | 3 High 4 High | ? ? | 3 Insurance in place 4 Insurance in place | 3 Low 4 Low | 3 NFA 4 NFA |
|  | - IT system failure | 5 High | 5 Low | Reputation Finance | 5 Anti virus and back up of data and maintenance contract | 5 Low | 5 NFA |
|  | - Pandemic illnesses | 6 Medium | 6. High | ? | 6. Masks, gloves, antiseptic wipes, contingency plan | 6. Medium | 6. Continued monitoring, apply State recommendations |
| 8 | Failure to act in accordance with the IALA Constitution | Low | High | Liability | Structure of Constitution and its regular review Legal Advisory Panel gives legal advice to Council and other IALA bodies | Low | None |
| 9 | Relocation project 1 Financial | 1 Low | 1 High | N/A | 1 Subsidy from France | 1 Medium | 1 completed |
|  | 2 Project timing | 2 Medium | 2 Medium | N/A | 2 Project plan meets current requirements Offer from DaMSA to host initial meetings Offer to provide alternative arrangements by France Space may be available for daily work if able to move in early | 2 Medium | 2 completed |

**  This agreement shall be governed by and constructed according to French Law.  All disputes arising from or in connection with this agreement shall be referred to the respective courts of law in the city of Versailles.

***************