## Slide 1: The Academy Update
Presentation to ANM
Stephen Bennett; Programme Manager
14 November 2012

## Slide 2: The Academy
“The IALA World-Wide Academy (WWA) is the vehicle by which IALA delivers training and capacity building”
In June 2012 IMO commended IALA on the establishment of The Academy, and requested that it be kept updated on the work carried out jointly between the IHO, IALA and IMO in the area of the UN capacity-building “Delivering as One” initiative
Key role played by IALA Committees enables the Academy to deliver both training and CB

## Slide 3: Academy Deliverables
Training and Model Courses
  VTS courses – V-103 series
  AtoN courses – E-141 Ed 2 (December 2012)
    AtoN Manager Overview – E-141/1
    One month AtoN Level 1 Manager course at IALA in March 2014
    AtoN Technician Overview – IALA WWA L2.0
    30 specialised model courses – L2.1.1 to L2.11.5
  Awareness seminars for Senior Managers – E-141/2
  Risk Management Model Courses – E141/3;4 …….
Capacity Building under the “4As” strategy

## Slide 4: The “4As”
Stage 1: Raising AWARENESS through targeted “Level 1+” seminars using a pre-seminar questionnaire
Stage 2: Request by newly aware States for ASSESSMENT of needs leading to…..
Stage 3: ANALYSIS of requirements including the use of available AIS data from all sources to give……..
Stage 4: Recommended ACTIONS to achieve full compliance

## Slide 5: Capacity Building Regions
Region | Target States
East Asia | 4
Eastern Atlantic | 19
Meso-America and Caribbean | 19
North Indian Ocean | 10
ROPME Region | 4
Southern Africa and Islands | 8
South-west Pacific | 11* (8 attended in Sydney)

## Slide 6: Capacity Building Progress
 | 2012 | Month | 2013 | 2014 | 2015
Stage 1 | Bahrain Cape Town Mauritius Thailand Sydney E Atlantic (Portugal) Guatemala | January June September September November November November | West Africa Columbia Burma North Indian Ocean E Asia Singapore Indonesia | Level 1 AtoN Manager course India Seminar Conference | Level 1 AtoN Manager course
Stage 2 |  |  | Cameroon Mauritius Madagascar Qatar SW Pacific | Caribbean Indian Ocean East Atlantic East Asia SW Pacific | East Asia SW Pacific Southern Africa

## Slide 7: Register of IALA Experts
Potential experts to be nominated by National Members or by individual application
Forms available on the Academy website
Applications to be vetted by panel from appropriate committee
Council to endorse experts
Endorsement to be reviewed after specified time
Remuneration at UN day rates

## Slide 8: Training and Accreditation
More Competent Authorities follow V-103 T&A process
  14 States in Oct; 16+ by VTS-36
E-141 T&A process taking shape
Level 1 AtoN Manager courses in French and English
Level 2 Technician Syllabus complete by EEP-21
Rolling review of the 30 L2 model courses
All T&A publications and documents available on new website

## Slide 9: AtoN Manager Certification – Grandfather Clause in E-141
“For an interim period of time which expires on 31 December 2014, the Competent Authority may deliver a Certificate Level 1 to any manager and engineer, or a Certificate Level 2 to any technician, having a minimum of 3 years of experience in the function for which they apply, within the last 5 years prior to submission of the application to the certification.”

## Slide 10: Summary
Academy First year exceeded expectations
Training procedures well established
Training documentation to be complete by mid 2013
Capacity Building 4As strategy delivering real results
Experts required to meet CB demands
Consider the Grandfather Clause
None of the above could have been achieved without Committee support