## Sheet1
Committee 2014 -2018 proposed work items | [9 empty] | Task Develop Doc,Perm Task,Liaison,Other |  |  |  |  | ANM21-12.1 Formerly ANM20/C&VC/WP1
Type | Reference | Name | Size | Current Edition No. | Last Updated | work load, high,Med Low | Priority High,Med,Low | Progress % | Complete Y/N | ANM | EEP | VTS | LAP | e-Nav | Review or Update Comments
Strategy |  | Ensure Committees complete all previous work items
|  | committees to complete any task in the 10-14 work program that is delayed and carried forward to post 2014 conference - Marine Spatial planning | n/a |  |  | M | H |  |  | O | x | x | x | x | With eNav in particular taking twists and turns at IMO one or two work items have slowed to await IMO developments ie virtual AIS aton. Tasks relating to these matters may overspill into 14-18 program.
Strategy |  | To ensure IALA publications remain relevant and up to date
Navguide | [5 empty] | H | H |  |  | DD |  |  |  |  | Undertake 4 yearly review of the IALA Navguide to be published at Conference in 2018
Guideline | 1005 | On contracting out Aids to Navigation Services | 13 pages | 2 | 2005-12-01 | L | L |  |  | DD
Guideline | 1020 | On training related to aids to navigation | 47 pages | 1.1 | 2005-12-01 | L | H |  |  | DD |  |  |  |  | related to WWA - may be withdrawn or incorporated with WWA
Guideline | 1033 | On the provision of aids to navigation for different classes of vessels, including high speed craft | 6 pages | 1 | 2003-12-01 | L | M |  |  | DD |  |  |  |  | Developments in Korea on Wing in ground craft need to be included in a revised guideline
Guideline | 1046 | On a Response Plan for the Marking of New Wrecks | 8 pages | 1 | 2005-06-01 | L | H |  |  | DD |  |  |  |  | To take into account the imminet ratifcation of the IMO Wreck removal convention include floating debri Refer ANM 20/WG1/WP1
Guideline | 1050 | On the Management and Monitoring of AIS Information | 8 pages | 1 | 2005-12-01 | M | H |  |  | DD |  |  |  |  | Implications of IMO corrospondence group to be taken into account
Guideline | 1051 | On the Provision of Aids to Navigation in built up areas | 8 pages | 1 | 2005-12-01 | L | L |  |  | DD
Guideline | 1054 | On Preparing for a Voluntary IMO Audit on Aids to Navigation Service Delivery | 19 pages | 1 | 2006-12-01 | L | H |  |  | DD |  |  |  |  | To be updated to reflect the compulsory nature of IMO audits. Mandatory in 2015
Guideline | 1055 | On Preparing for a Voluntary IMO Audit on Vessel Traffic Service Delivery | 20 pages | 1 | 2006-12-01 | [6 empty] | DD |  |  | Should the VTS committee own this document?
Guideline | 1057 | Use of Geographical Information Systems by Aids to Navigation Authorities | 10 pages | 1 | 2007-12-01 | M | L |  |  | DD
Guideline | 1069 | Synchronisation of Lights | 31 pages | 1 | 2009-05-01 | L | M |  |  | DD |  |  |  |  | To incorpoarate lessons learnt from practical use of the synchronised lights.
Guideline | 1079 | On Establishing and Conducting User Consultancy by Aids to Navigation Authorities | 22 pages | 1 | 2009-12-01 | L | L |  |  | DD |  |  |  |  | Possible WWA model course to be developed from this revision
Guideline | 1081 | On Virtual AtoN | 19 pages | 1 | 2010-03-01 | M | H |  |  | DD |  |  |  |  | To incorporate developments at IMO corrospondance group
Recommendation | O-118 | For the recording of aids to navigation positions | 3 pages | 1.1 | 2005-12-01 | L | L |  |  | DD
Recommendation | O-134 | On the IALA Risk Management Tool for Ports and Restricted Waterways | 22 pages | 2 | 2009-05-01 | L | H |  |  | DD |  |  |  |  | To reflect updates in PAWSA accrediattion and IWRAP
Recommendation | O-143 | Virtual Aids to Navigation | 7 pages | 1 | 2010-03-01 | L | H |  |  | DD |  |  |  |  | May be incorpoared into 1081To incorporate developments at IMO corrospondance group
Recommendation | E111 | Port traffic signals |  |  |  | L | M |  |  | DD |  |  |  |  | To be reviewed to include guidance on port closure signals
Recommendation | O-138 | Use of GIS and Simulation by Aids to Navigation Authorities | 7 pages | 1 | 2007-12-01 | L | M |  |  | DD |  |  |  |  | to consider if this document has been superseded by 1058 amendmants and supplement.
Strategy |  | Identify gaps in IALA technical coverage and ensure where necessary new publications are developed
Recommendation |  | Develop recommendation on portable marine devices |  |  |  | L | L |  |  | DD |  |  |  |  | There is a growing proliferation of unregulated portable devices ostensibly for the leisure industry which are leaking into use onboard SOLAS vessels eg unregulated charts, non wheel marked tablets etc which jave a potential to put vessel and mariner at risk.
Guideline |  | Develop guidelines for the management of Aton in envormentally protected areas |  |  |  | H | H |  |  | DD |  |  |  |  | Globally there is an expanding network of protected areas both on and off shore which have legal restriction of the activitieds permitted during particular period or at all. Aton management authorities now have to work with the relevant enviromental bodies to ensure Aton can be maintained, established or varied. Guidance from authorities which have experience of this for countries/ regions deloping policy on this matter would be beneficial
EEP? |  | Develop guidance on the requirement for daymarks on floating and fixed Aton |  |  |  | L | M |  |  | DD |  |  |  |  | a gap analysis has identified there is little guidance on daymark properties of Aton
|  | Develop guidance on disaster recovery |  |  |  | M | H |  |  | DD |  |  |  |  | Recent events in Japan and other countries have demonstarted that IALA should provide advise on distaster recovery preparations
|  | Develop Guidance on pictograms for use on special marks |  |  |  | L | M |  |  | DD |  |  |  |  | as a result of comments on the MBS it has been ientified that use of pictograms should be defined further and standardisation recommended
|  | Develop guidance on the marking of overhead power lines |  |  |  | L | L |  |  | DD |  |  |  |  | ANM Task 10 of the 10-14 programme identified a separate guideline/reccomendation was required for the marking of overhead power cables
Strategy |  | eNavigation
|  | Incorporpoate further developments in eNavigation at IMO into existing or new IALA documentation advising Aton Authorities and the mariner of implications and implementation. |  |  |  | H | H |  |  | DD |  |  |  |  | During 2014-18 work prtogram IMO is expected to make key descsions on eNavigation. IALA documentation needs to be updated to reflect what is actually going to happen as opposed to what may happen or is possible.
Startegy |  | S100 -
|  | Continue to progress with other committee the IALA registry for S100 |  |  |  | M | H |  |  | L |  |  |  |  | work only to be within the technical capability of the committee.
Strategy |  | Capacity building
|  | Support the development and expansion of the WWA by providing model courses and technical expertise |  |  |  | M | H |  |  | L
Strategy |  | IALA analysis of SOLAS compliance
|  | Update the IALA Questionairre at ANM 28 in advance of conference for the 18-22 work programme |  |  |  | L | H |  |  | O