## 2014-18 ANM
Committee 2014 -2018 proposed work items | [9 empty] | Task Develop Doc,Perm Task,Liaison,Other | [5 empty] | ANM21-xxxx Formerly ANM21-12.1
Type | Reference | Name | Size | Current Edition No. | Last Updated | work load, high,Med Low | Priority High,Med,Low | Progress % | Complete Y/N | ANM | EEP | VTS | LAP | e-Nav | Sec | Review or Update Comments
Strategy |  | Ensure Committees complete all previous work items
|  | Develop a recommendation for navigational safety matters within Marine Spatial Planning |  |  |  | M | H |  |  | DD | x | x | x | x | x | Work coomenced at MSA workshop and continued in ANM21 requires completeion ANM22 & 23
Strategy |  | Transform the existing documents to suit IGO status
Navguide | [5 empty] | H | H |  |  | DD | [5 empty] | Undertake 4 yearly review of the IALA Navguide to be published at Conference in 2018
ALL ANMDocs |  | Format to new IALA format |  |  |  | H | H | [8 empty] | To meet transition to IGO staus
Guideline | 1005 | On contracting out Aids to Navigation Services | 13 pages | 2 | 2005-12-01 | L | L |  |  | DD
Guideline | 1033 | On the provision of aids to navigation for different classes of vessels, including high speed craft | 6 pages | 1 | 2003-12-01 | L | M |  |  | DD | [5 empty] | Is there a need for a guideline that is specific to high speed craft? This information should be built into the risk analysis when designing or reviewing an aids to navigation system. All classes of vessels, including high speed craft, require special considerations. A review of this document is needed to determine if it is redundant given Guideline 1018 on Risk Management already gives consideration to high speed craft. Developments in Korea on Wing in ground craft need to captured
Guideline | 1046 | On a Response Plan for the Marking of New Wrecks | 8 pages | 1 | 2005-06-01 | L | H |  |  | DD | [5 empty] | To take into account the imminet ratifcation of the IMO Wreck removal convention include floating debri Refer ANM 20/WG1/WP1 Recommend removal of specific wreck incidents.
Guideline | 1050 | On the Management and Monitoring of AIS Information | 8 pages | 1 | 2005-12-01 | M | H |  |  | DD | [5 empty] | Implications of IMO corrospondence group to be taken into account
Guideline | 1051 | On the Provision of Aids to Navigation in built up areas | 8 pages | 1 | 2005-12-01 | L | L |  |  | DD | [5 empty] | Is there a need for a guideline that is specific to AtoN in built-up areas? This information should be built into the risk analysis when designing or reviewing an aids to navigation system. All areas, including those built up, require special considerations. A review of this document is needed to determine if it is redundant given Guideline 1018 on Risk Management already gives consideration to bakcground lighting.
Guideline | 1052 | On Quality Management in Aids to Navigation Service Delivery (revokes (guideline 1001 & 1003) | 29 pages | 2 | 2006-12-01 | L | L |  |  | DD | [5 empty] | Review in progress ANM 17-21. Assigned to WG2 as Task 8 at ANM 17. Complete ANM 21? Will need quick review in 14-18 to account for e-Nav
Guideline | 1054 | On Preparing for a Voluntary IMO Audit on Aids to Navigation Service Delivery | 19 pages | 1 | 2006-12-01 | L | H |  |  | DD | [5 empty] | To be updated to reflect the compulsory nature of IMO audits. Mandatory in 2015
Guideline | 1057 | Use of Geographical Information Systems by Aids to Navigation Authorities | 10 pages | 1 | 2007-12-01 | M | L |  |  | DD
Guideline | 1062 | On the establishment of AIS as an Aid to Navigation | 18 pages | 1 | 2008-12-01 | M | M |  |  | DD | [5 empty] | There are guidelines 1062 and 1084 and recommendation A-126 that all speak to establishment, authorization and use of AIS. All three should be reviewed with the goal of consolidating this into one document. Both 1084 and A-126 have recently been updated and should not require a review.14-18
Guideline | 1069 | Synchronisation of Lights | 31 pages | 1 | 2009-05-01 | L | M |  |  | DD | [5 empty] | To incorpoarate lessons learnt from practical use of the synchronised lights.
Guideline | 1079 | On Establishing and Conducting User Consultancy by Aids to Navigation Authorities | 22 pages | 1 | 2009-12-01 | L | L |  |  | DD | [5 empty] | Possible WWA model course to be developed from this revision
Guideline | 1081 | On Virtual AtoN | 19 pages | 1 | 2010-03-01 | M | H |  |  | DD | [5 empty] | To incorporate developments at IMO corrospondance group
Recommendation | O-118 | For the recording of aids to navigation positions | 3 pages | 1.1 | 2005-12-01 | L | L |  |  | DD | [5 empty] | incorporate USCG recent changes
Recommendation | O-134 | On the IALA Risk Management Tool for Ports and Restricted Waterways | 22 pages | 2 | 2009-05-01 | L | H |  |  | DD | [5 empty] | To reflect updates in PAWSA accrediattion and IWRAP and any inclusion of SAMSON
Recommendation | O-143 | Virtual Aids to Navigation | 7 pages | 1 | 2010-03-01 | L | H |  |  | DD | [5 empty] | May be incorpoared into 1081To incorporate developments at IMO corrospondance group
Recommendation | E111 | Port traffic signals |  |  |  | L | M |  |  | DD | [5 empty] | To be reviewed to include guidance on port closure signals
Recommendation | O-138 | Use of GIS and Simulation by Aids to Navigation Authorities | 7 pages | 1 | 2007-12-01 | L | M |  |  | DD | [5 empty] | to consider if this document has been superseded by 1058 amendmants and supplement.
Strategy |  | Transform the existing documents to suit IGO status (New documents)
Guideline |  | Develop guidelines for the management of Aton in envormentally protected areas |  |  |  | H | H |  |  | DD | [5 empty] | Globally there is an expanding network of protected areas both on and off shore which have legal restriction of the activitieds permitted during particular period or at all. Aton management authorities now have to work with the relevant enviromental bodies to ensure Aton can be maintained, established or varied. Guidance from authorities which have experience of this for countries/ regions deloping policy on this matter would be beneficial
|  | Develop guidance on disaster recovery |  |  |  | M | H |  |  | DD | [5 empty] | Recent events in Japan and other countries have demonstarted that IALA should provide advise on distaster recovery preparations
|  | Develop Guidance on pictograms for use on special marks |  |  |  | L | M |  |  | DD | [5 empty] | As a result of comments on the MBS, it has been identified that use of light rhythms and pictograms should be defined further to achieve uniformity and enable mariners to distinguish between various applications of special marks.
|  | Develop guidance on the marking of overhead power lines |  |  |  | L | L |  |  | DD | [5 empty] | ANM Task 10 of the 10-14 programme identified a separate guideline/reccomendation was required for the marking of overhead power cables
Strategy |  | Lay ground work for ship/shore interopability in e-Nav
|  | Incorporpoate further developments in eNavigation at IMO into existing or new IALA documentation advising Aton Authorities and the mariner of implications and implementation. |  |  |  | H | H |  |  | DD | [5 empty] | During 2014-18 work prtogram IMO is expected to make key descsions on eNavigation. IALA documentation needs to be updated to reflect what is actually going to happen as opposed to what may happen or is possible.
|  | Continue to progress with other committee the IALA registry for S100 |  |  |  | M | H |  |  | L | [5 empty] | work only to be within the technical capability of the committee.
Strategy |  | Promote the merits of IALA
|  | Support the development and expansion of the WWA by providing model courses and technical expertise |  |  |  | M | H |  |  | L
Strategy |  | IALA analysis of SOLAS compliance
|  | Update the IALA Questionairre at ANM 28 in advance of conference for the 18-22 work programme |  |  |  | L | H |  |  | O
Strategy |  | IALA RISK tool box
|  | Incorporate Samson into IWRAP |  |  |  | M | M | [8 empty] | For IALA risk steering group

## Docs managed by ANM
IALA Documents Managed by the ANM Committee corect to 15/10/13 | [5 empty] | ANM21-x.x.x
Formerly ANM21-9.9.1
Type | Reference No. | Name | Size | Current Edition No. | Last Updated | Review or Update Comments
Guideline | 1004 | On levels of service | 23 pages | 2 | 2013-05-01 | Completed ANM20
Guideline | 1005 | On contracting out Aids to Navigation Services | 13 pages | 2 | 2005-12-01 | No immediate updates identified during a high level review. Recommended for Work Plan 2014-2018
Guideline | 1018 | On Risk Management | 44 pages | 3 | 2013-05-01 | Completed ANM20
Guideline | 1020 | On training related to aids to navigation | 47 pages | 1.1 | 2005-12-01 | Guideline no longer available online. Was this replaced by the work on WWA?
Guideline | 1033 | On the provision of aids to navigation for different classes of vessels, including high speed craft | 6 pages | 1 | 2003-12-01 | Is there a need for a guideline that is specific to high speed craft? This information should be built into the risk analysis when designing or reviewing an aids to navigation system. All classes of vessels, including high speed craft, require special considerations. A review of this document is needed to determine if it is redundant given Guideline 1018 on Risk Management already gives consideration to high speed craft. Recommended for Work Plan 2014 - 2018.
Guideline | 1046 | On a Response Plan for the Marking of New Wrecks | 8 pages | 1 | 2005-06-01 | Recommend removal of specific wreck incidents. No other immediate updates identified. Recommended for Work Plan 2014-2018.
Guideline | 1050 | On the Management and Monitoring of AIS Information | 8 pages | 1 | 2005-12-01 | No immediate updates identified during a high level review. Recommended for Work Plan 2014-2018
Guideline | 1051 | On the Provision of Aids to Navigation in built up areas | 8 pages | 1 | 2005-12-01 | Is there a need for a guideline that is specific to AtoN in built-up areas? This information should be built into the risk analysis when designing or reviewing an aids to navigation system. All areas, including those built up, require special considerations. A review of this document is needed to determine if it is redundant given Guideline 1018 on Risk Management already gives consideration to bakcground lighting. Recommended for Work Plan 2014 - 2018.
Guideline | 1052 | On Quality Management in Aids to Navigation Service Delivery (revokes (guideline 1001 & 1003) | 29 pages | 2 | 2006-12-01 | Review in progress ANM 17-21. Assigned to WG2 as Task 8 at ANM 17. Complete ANM 21? Will need quick review in 14-18 to account for e-Nav
Guideline | 1054 | On Preparing for a Voluntary IMO Audit on Aids to Navigation Service Delivery | 19 pages | 1 | 2006-12-01 | Has the process for IMO audits changed in the past five years? If unsure, assign task to investigate if it has. If yes, a review and update is needed. Given the low frequency of voluntary IMO audits, it is recommended for Work Plan 2014 - 2018.
Guideline | 1057 | Use of Geographical Information Systems by Aids to Navigation Authorities | 10 pages | 1 | 2007-12-01 | No immediate updates identified during a high level review. Recommended for Work Plan 2014-2018
Guideline | 1058 | Use of Simulation as a Tool for Waterway Design and Aids to Navigation Planning | 19 pages | 2 | 2011-06-01 | Completed ANM 16. Website references Edition 1 and 2. Have IALA correct this by removing edition 1 from the list.
Guideline | 1062 | On the establishment of AIS as an Aid to Navigation | 18 pages | 1 | 2008-12-01 | There are guidelines 1062 and 1084 and recommendation A-126 that all speak to establishment, authorization and use of AIS. All three should be reviewed with the goal of consolidating this into one document. Both 1084 and A-126 have recently been updated and should not require a review.14-18
Guideline EEP? | 1069 | Synchronisation of Lights | 31 pages | 1 | 2009-05-01 | No immediate updates identified during a high level review. Recommended for Work Plan 2014-2018. Technical portion of document may need to be assigned to another committee.
Guideline | 1078 | On a minimum comprehensive mix of AtoN in fairways | 14 pages | 1 | 2011-06-01 | Completed ANM 16
Guideline | 1079 | On Establishing and Conducting User Consultancy by Aids to Navigation Authorities | 22 pages | 1 | 2009-12-01 | No immediate updates identified during a high level review. Recommended for Work Plan 2014-2018.
Guideline | 1081 | On Virtual AtoN | 19 pages | 1 | 2010-03-01 | Document reviewed ANM20 but will require next review 2014-18 to allow for changes at IMO
Guideline | 1084 | On the Procedure for the Authorisation of AIS AtoN | 8 pages | 1 | 2011-06-01 | Completed ANM 16
Guideline EEP? | 1086 | On Global sharing of maritime data |  | 1 | 2012-06-01
Guideline EEP? | 1090 | On audible signals |  | 1 | 2012-12-01
Guideline | 1096 | Anticipated User e-Nav requirements for AtoN Authorities |  | 1 | 2013-05-01 | Complete ANM20
Guideline | ? | Application of maritime surface picture for analysis in risk assessment and provision of AtoN |  |  |  | New guideline underdevelopment complete ANM21?
Guideline | 1097 | Technical features and technology relevant for simulation of Aton |  | 1 | 2013-05-01 | Complete ANM20
Recommendation | A-126 | Use of AIS in Marine Aids to Navigation Service | 26 pages | 1.5 | 2011-06-01 | Completed ANM 16
Recommendation | O-104 | On ‘Off Station’ signals for major floating aids | 5 pages | 2 | 2012-06-01 | Complete ANM 19
Recommendation | O-113 | For the marking of fixed bridges over navigable waters | 6 pages | 2 | 2011-12-01 | Complete ANM18
Recommendation | O-118 | For the recording of aids to navigation positions | 3 pages | 1.1 | 2005-12-01 | No immediate updates identified during a high level review. Recommended for Work Plan 2014-2018.
Recommendation | O-130 | On Categorisation and Availability Objectives for Short Range Aids to Navigation | 8 pages | 2 | 2011-06-01 | Completed ANM 16
Recommendation | O-132 | On Quality Management for Aids to Navigation Authorities | 4 pages | 2 | 2006-12-01 | Complete ANM20 but needs review 14-18 fot eNav content
Recommendation | O-134 | On the IALA Risk Management Tool for Ports and Restricted Waterways | 22 pages | 2 | 2009-05-01 | No immediate updates identified during a high level review. Recommended for Work Plan 2014-2018.
Recommendation | O-138 | Use of GIS and Simulation by Aids to Navigation Authorities | 7 pages | 1 | 2007-12-01 | No immediate updates identified during a high level review. Significant work has been undertaken to update the guidelines related to simulation software. Recommend for Work Plan 2014 - 2018.
Recommendation | O-139 | The Marking of Man-Made Offshore Structures |  | 1 | 2008-12-01 | Review in progress ANM 15-17. Assigned to WG1 as Task 12 at ANM 17. complete ANM21?
Recommendation | O-143 | Virtual Aids to Navigation | 7 pages | 2 | 2013-05-01 | Complete ANM20 but needs review 14-18 fot eNav content
| N/A | IALA Questionaire |  |  |  | Under review ANM 21 complete?
Manual | N/A | IALA Navguide |  |  | 2010-05-01 | Under review ANM 21 complete?
Manual | N/A | MBS |  |  | 2010-05-01 | No review intended. Supplementary guidance inserted in Navguide
Note: Many documents with release date of December 2005 were only reformatted to comply with an updated IALA template.