# ACTION PLAN FOR

# THE REVISION OF THE NAVGUIDE

The following is an action plan to implement the changes to the NAVGUIDE:

| Chapter 1 - IALA | - Section 1.1-Introduction: This will be performed by the ANM-WG2 by ANM6 (April 2005). - Sections 1.2-Membership and 1.3-IALA Structure: It is requested that the IALA Secretariat revise sections 1.2 and 1.3 by ANM5 (October 2004). - Section 1.4-IALA Publications: It is proposed that the documentation hierarchy, as defined during ANM1 (document ANM2/13/info1) should be presented to the Council for approval and for the distribution of work to the IALA Secretariat and to the ANM Committee. The proposal will include details for the different documents as well as a numbering system. |
| --- | --- |
| Chapter 2 – Concepts and accuracy of navigation | - The revision of this chapter will begin within the WG2 during ANM4 (April 2004) and should be completed during ANM5 (October 2004). |
| Chapter 3 – Aids to Navigation | - The revision of the section “Introduction and Definition of Aids to Navigation “ will be performed by ANM-WG2 during session 3 and 4. - The other sections are to be assigned to other committees. Please see document ANM2/9/1rev1 for more details. The revision of the section should be completed for session 5 (October 2004). |
| Chapter 4 – Other facilities | - The revision of this chapter will begin within the WG2 during ANM3 (October 2003) and should be completed during ANM4 (April 2004). |
| Chapter 5 – Power Supplies | - The revision of this section is to be performed by EEP by session 5 (October 2004). |
| Chapter 6 – Management Issues | - The revision of this chapter will begin within the WG2 during ANM3 (October 2003) and should be completed during session 5(October 2004). |