Program Evaluation Proposal – IALA MBS

# Background

At the XVIth IALA Conference in Shanghai, PRC, in May 2006 a number of presentations touched on the role of the IALA Maritime Buoyage System (IALA MBS) and the provision of Aids to Navigation in a Digital World.  This led the conference to conclude that:

Although the maritime buoyage system has served the maritime community well since its inception in the 1970s, it is time to review the system in light of changes in the shipping environment and the development of digital aids to navigation.  (Conclusion 5)

In accordance with the conclusion, IALA Recommended that:

IALA review the maritime buoyage system in consultation with all related organizations and user groups. (Recommendation 4)

The IALA Aids to Navigation Management Committee has been tasked with the review, and this proposal provides the guidance document for carrying out a logical, complete and timely review.  The proposal provides target dates and deliverables, and indicates the completion of the review in time for approval by Council in December 2009 and presentation of results to the XVIIth IALA Conference to be held in South Africa, March 2010.

# Program Evaluation Proposal

When approaching the evaluation of the IALA MBS, it is imperative that the environment in which the MBS is now implemented is included.  Any review of the MBS must be seen in light of the provision of the optimum mix of all aids to navigation to ensure a safe waterway to reflect the density of traffic and the level of risk (ref SOLAS Chapter V, Regulation 13

The proposed evaluation looks at the function of buoys and other aids to navigation, how they are used in navigation at present and how they may be used as the practice of marine navigation develops.  As presented at the IALA Conference, buoys seem to have evolved from being an aid to navigation to being a ‘cross-check’ tool.  The evaluation has been designed to provide both quantitative and qualitative assessment of AtoN requirements.

# Steps in the IALA Aids to Navigation Evaluation

A four step process is proposed:

Step 1 – Defining the scope

Step 2 – Setting the process

Step 3 – Implementing the process

Step 4 – Evaluating the results

## Step 1 – Defining the Scope

Working within the context of safety of navigation and protection of the environment, the IALA AtoN evaluation will focus on AtoN programmes – the requirement for the service vs. the service provided.  This will include existing elements in AtoN; the existing and emerging navigational environment including vessel traffic trends and risk analysis; and best practices in the provision of AtoN to respond to the traffic requirements and level of risk.  Through the review, a gap analysis will be completed and options for determining the optimum use of aids to navigation, including the use of the MBS, will be provided.

## Step 2 – Setting the process

Setting the process will follow the logic model for program evaluation, assessing the goals of the provision of AtoN, indicating the strategies for the provision of AtoN, identifying the stakeholders (users, service providers, equipment providers), listing the developments in navigation technology that affects aids to navigation, identifying the existing needs of the stakeholders, projecting the future needs of the stakeholders (taking into account the development of e-navigation) and finally presenting options to provide the optimum mix of aids to navigation to respond to the requirements of SOLAS, meeting the needs of the stakeholders.

The process will include four phases: a research and review phase to identify the existing situation and set the base line; a consultative phase to gather input from stakeholders; an assessment phase where the data collected will be critically reviewed and options suggested; and, a validation phase, where stakeholders have an opportunity to comment on the results of the evaluation and rank the options.

## Step 3 – Implementing the Process

Implementing the process will require a phased implementation.

### Phase 1 – Research / Review

Phase 1 will encompass a review of existing publications and past studies / evaluations of AtoN systems, inlcuding the MBS.

Phase 1 deliverables will include:

- Listing of relevant studies

- Initial analysis of results of relevant studies

- Basis for developing informed questionnaires / presentations for use in Phase 2.

- List of stakeholders (to be consulted in Phase 2)

Phase 1 will last for approximately six months and encompass two meetings of the ANM Committee.

### Phase 2 - Consultation

In Phase 2 questionnaires and presentations will be provided to stakeholders (as far as possible through existing presentation opportunities by ANM members) and other means of consulting the stakeholders identified in Phase 1.

Phase 2 deliverables will include:

- Listing of presentations provided / indication of audience, target stakeholder group addressed

- Questionnaires – designed / provided / completed / returned

- Initial analysis of returned questionnaires

Phase 2 will overlap Phase 1 in that the questionnaire will be developed / agreed at the second meeting of the ANM Committee following acceptance of this evaluation proposal.

Phase 2 will run for 12 months and encompass three meetings of the ANM Committee.

### Phase 3 – Analysis

Phase 3 will include analysis of the results of Phase 2 consultations, combined with analysis of Phase 1 research.

Phase 3 deliverables will include

- Statement indicating present situation with regards to the provision of AtoN, including the MBS

- Analysis of the results of the consultation

- List of key findings from the consultation

- Identification of issues / ‘problems’ with existing provision of AtoN (as identified)

- Identification of best practices with existing provision of AtoN (as identified)

- Proposals for options with regards to the provision of AtoN

Phase 4 will run for approximatelysix months and encompass two meetings of the ANM Committee.

### Phase 4 – Validation of Analysis

Phase 4 provides an opportunity for stakeholders involved in Phase 2 to view the results and provide comment on the proposed options.  Phase 4 should be seen as an opportunity to refine the results and ensure realistic and workable options are provided in the evaluation report, including indication of the recommended option.

- Deliverables for Phase 4:

- Collated responses from stakeholder comments on the results of Phase 3

- Indication of recommended option

Phase 4 will run for approximately 6 months and encompass two ANM Committee meetings.

## Step 4 – Presentation of results

Step 4 is the final compilation of the report and presentation of results.  The final evaluation report will be prepared for presentation to IALA Council and, as approved, the next IALA Conference.

# Conclusion

The evaluation of the IALA MBS, encompassing the environment in which it is implemented, has been identified as a work item for the ANM Committee.  The proposal for the evaluation presented here provides a means to carryout research on the existing situation, consult with stakeholders, analyse the results and then validate the results through further consultation.  The timing for the evaluation is tight, noting the meeting schedule and the ongoing requirements of ANM Committee members.

IALA AtoN Evaluation Proposal

| Element |  | Deliverables | Time line/ANM meeting |
| --- | --- | --- | --- |
| Step 1 – Defining the scope |  | Program Evaluation proposal document presented to Council for approval. | ANM 9 – April 2007 / IALA Council June 2007 |
| Step 2 – Setting the process |  | Process included in Program Evaluation Proposal document, presented to Council for approval. | ANM 9 – April 2007 / IALA Council June 2007 |
| Step 3 – Implementing the Process | Phase 1 – Research / Review | Listing of relevant studies Initial analysis of results of relevant studies Basis for developing informed questionnaires / presentations for use in Phase 2. List of stakeholders (to be consulted in Phase 2) | ANM 9 – April 2007 ANM 10 – Oct 2007 |
|  | Phase 2 – Consultation | Listing of presentations provided / indication of audience, target stakeholder group addressed Designed / completed Questionnaires Initial analysis of returned questionnaires | ANM 10 – Oct 2007 ANM 11 – April 2008 ANM 12 – Oct 2008 |
|  | Phase 3 - Analysis | Statement indicating present situation with regards to the provision of AtoN, including the MBS Analysis of the results of the consultation List of key findings from the consultation Identification of issues / ‘problems’ with existing provision of AtoN (as identified) Identification of best practices with existing provision of AtoN (as identified) Proposals for options with regards to the provision of AtoN | ANM 12 – Oct 2008 ANM 13 – April 2009 |
|  | Phase 4 - Validation | Collated responses from stakeholder comments on the results of Phase 3 Indication of recommended option | ANM 13 – April 2009 ANM 14 – Oct 2009 |
| Step 4 – Presentation of Results |  | Compilation of Report Presentation of Results to IALA Council / IALA Conference | ANM 14 – Oct 2009 / IALA Council Dec 2009 / IALA Conference March 2010 |