Overall status of the ARM Committee 2014-2018 Work Programme after ARM6:

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Task** | **Start Session** | | | **Planned End Session** | | | **Revised End Session** | | | **Progress Indicator** | | | | | | **Status Overview** | |
| **Green** | | **Yellow** | | **Red** | |  | | |
| **TD#1 – Requirements for AtoN systems** |  | |  | | |  | | |  | | | |  | |  | |  | | |
| 1.1.1 Contribute to standards generated by Secretariat | 4 | 7 | | |  | | |  | | | |  | |  | | Completed ARM6 | | | |
| 1.1.2 Workshop on AIS AtoN (real and virtual) | 2 | 4 | | | 5 | | |  | | | |  | |  | | Initiated ARM2  Completed ARM5 | | | |
| 1.1.3 Guideline on the marking of wrecks as defined by the Nairobi Wreck Convention | 4 | 7 | | |  | | |  | | | |  | |  | |  | | | |
| 1.1.4 Guideline on the use of pictograms on AtoN | 3 | 5 | | | 7 | | |  | | | |  | |  | | Commenced ARM3  Completed ARM6 | | | |
| 1.1.5 |  |  | | |  | | |  | | | |  | |  | | Task merged with 1.1.4 ARM3 | | | |
| 1.1.6 Guideline on the use of mobile AtoN | 4 | ~~7~~ | | | WP 18-22 | | |  | | | |  | |  | |  | | | |
| 1.2.1 Populate S-100 as requested by ENAV Committee | 1 | 7 | | |  | | |  | | | |  | |  | | Commenced ARM1  Ongoing WP 18-22 | | | |
| **TD#2 – Management for AtoN services** |  |  | | |  | | |  | | | |  | |  | |  | | | |
| 2.1.1 Develop guidance for AtoN authorities on disaster recovery | 1 | 4 | | | 6 | | |  | | | |  | |  | | Commenced ARM1  Completed ARM6 | | | |
| 2.1.2 Contribute to standards generated by Secretariat | 4 | 7 | | |  | | |  | | | |  | |  | | Completed ARM6 | | | |
| 2.1.3 Consider guidance for authorities on the use of enavigation services | 4 | 7 | | |  | | |  | | | |  | |  | | Stopped due to ENAV progression | | | |
| 2.5.1 Develop guidance on the management of AtoN in environmentally protected areas | 2 | 7 | | |  | | |  | | | |  | |  | | Commenced ARM2 | | | |
| **TD#3 – Marine Spatial Planning** |  |  | | |  | | |  | | | |  | |  | |  | | | |
| 3.1.1 Develop guidance for AtoN authorities on the use of Marine Spatial Planning | 1 | 4 | | | 6 | | |  | | | |  | |  | | Commenced ARM1  Completed ARM6 | | | |
| 3.4.1 Oversee development of Risk Management Toolbox | 4 | 7 | | |  | | |  | | | |  | |  | | New task ARM4 WG3  Ongoing WP 18-22 | | | |
| 3.4.2 Develop guidance on PAWSA | 4 | 7 | | |  | | |  | | | |  | |  | | New task ARM4 WG3  Completed ARM6 | | | |
| 3.4.3 Develop guidance on SQUART / ISTAR | 4 | 7 | | |  | | |  | | | |  | |  | | New task ARM4 WG3 | | | |
| 3.4.4 Develop guidance on use of IWRAP | 5 | 7 | | |  | | |  | | | |  | |  | | New task ARM4 WG3  Completed ARM6 | | | |
| 3.4.5 Training / workshop / seminar in association with WWA | 5 | ~~7~~ | | | WP 18-22 | | |  | | | |  | |  | | New task ARM4 WG3 | | | |
| 3.4.6 IALANET | 5 | 7 | | |  | | |  | | | |  | |  | | New task ARM4 WG3  Ongoing WP 18-22 | | | |
| **TD#4 –** **International coordination and liaison** |  |  | | |  | | |  | | |  | | |  | |  | |
| 4.1.1 |  |  | | |  | | |  | | |  | | |  | | Task cancelled ARM3 | |
| 4.2.1 |  |  | | |  | | |  | | |  | | |  | | Task cancelled ARM3 | |
| 4.2.2 Coordinate a limited review of the IALA Navguide to incorporate amended guidelines and recommendations and other necessary updates via wiki | 1 | 7 | | |  | | |  | | |  | | |  | | Commenced ARM1 | |
| 4.2.3 |  |  | | |  | | |  | | |  | | |  | | Task cancelled ARM3 | |
| 4.2.4 |  |  | | |  | | |  | | |  | | |  | | Task cancelled ARM3 | |
| 4.2.5 Amend IALA dictionary as appropriate including harmonisation of definition of AtoN | 1 | 7 | | |  | | |  | | |  | | |  | | Commenced ARM1  Completed ARM5 | |
| 4.2.6 Map existing ARM documentation to 7 overarching standards | 3 | 7 | | |  | | |  | | |  | | |  | | New task ARM3  Commenced ARM3  Completed ARM6 | |
| 4.2.7 Rewrite ARM documentation to meet new document structure in conjunction with IALA assistance | 3 | 7 | | |  | | |  | | |  | | |  | | New task ARM3  Commenced ARM3  Ongoing WP 18-22 | |