| No. | Risk Descriptor | Consequence | Risk Estimation (Prior to Mitigation) |  | Control & Treatment | Residual Risk EEP17/8/29 Status |  | Owned & Reviewed By |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Probability | Impact |  | Probability | Impact |  |
| 1 | Missed call from member of public | Important information on AtoN failure not received or delayed | Medium | Medium | Retain present 24 hour number Option 1 on message redirection to OPC Test system regularly | Low | Medium | HoM |
| 2 | Missed call / fax from IRCG | Important information on wreck, new danger or AtoN failure not received or delayed | Low | Medium | Retain present numbers Option 1 on message redirection to OPC Test system regularly Build relationship with IRCG. IRCG now emailing information to TSO and THOPC. | Very Low | Medium | HoM |
| 4 | Incorrect identification of station (colloquialisms, accents, etc) | Casualty not registered or incorrectly registered | Medium | Medium | OPC build and maintain list of colloquialisms Check list for calls 24hr Availability of Duty Inspector | Low | Medium | HoM |
| 5 | Incorrect identification of LATON | Casualty not registered or incorrectly registered | Low | Medium | LATON database available Check list for calls 24hr Availability of Duty Inspector | Very Low | Medium | HoM |
| 6 | Failure to initiate RNW | Mariners not advised of risk | Low | Medium | Experienced staff in OPC Fail safe handover procedures and checklists | Very Low | Medium | HoM |
| 7 | Incorrect assessment of wreck | Mariners not advised of risk | Medium | High | Experienced staff in OPC Charts and publications available 24hr Availability of Duty Inspector and ship for advice | Low | High | HoM |
| 8 | Unavailability of Duty Inspector | OPC cannot access advice or decision | Low | Medium | Call any other Inspector Call ship Experienced staff in OPC can act if required | Very Low | Medium | HoM |
| 9 | Loss of CIL RCMS monitoring connection to OPC | OPC can’t view AtoN status, alarm information | Very High | Medium | Fully redundant systems at both OPC and CIL for RCMS monitoring | Low | Medium |  |
| 10 | Loss of CIL AIS monitoring connection to OPC | OPC can’t view AtoN status, alarm information | Very High | Medium | Fully redundant systems at both OPC and CIL for AIS monitoring | Medium | Medium |  |
| 11 | Loss of CIL DGPS monitoring connection to OPC | OPC can’t view AtoN status, alarm information | High | Medium | DGPS can be monitored through RCMS system | Low | Medium |  |
| 12 | Incorrectly forwarded phone system out of hours | No out of hours phone support for CIL | Very High | Medium | Procedure to handover phone requires TSO to contact OPC via the CIL main number using a separate mobile | Medium | Medium |  |
| 13 | Unmanned building outside of office hours | Security, fire, flood risk. | High | High | Phone monitored security system and fire system installed, front gates locks. Flood detectors in server room connected to OPC monitoring display. | Medium | High |  |
| 14 | Failure of building power | Loss of all Monitoring, ICT and Building services | Low | High | Standby Generator available, all Mains/Generator alarms are monitored by OPC. | Very Low | High |  |
| 15 | Failure of server room chillers | Failure of Monitoring and ICT severs | Medium | High | Redundant Chillers installed. Redundant ICT and Monitoring servers in two server rooms | Very Low | High |  |
| 16 |  |  |  |  |  |  |  |  |

| Estimation | Description | Indicators | Consequence of Impact |
| --- | --- | --- | --- |
| Very High (Highly Probable) | Very likely to occur within 1year or more than 80% chance of occurrence. | Has occurred; likely to re-occur. | Financial impact on GLA/GLF likely to exceed £1M Major impact on GLAs’ delivery of operational services Major political, media and stakeholder concern Very low defensibility of realisation of risk Reinstatement to pre-risk condition extremely difficult requiring considerable resources and possible additional sanction from DfT. |
| High (Probable) | Likely to occur every 1 to 2 years or 50% to 80% chance of occurrence. | Likely to occur or has occurred. | Financial impact on GLA/GLF likely to be in region of £500K to £1M Significant impact on GLAs’ delivery of operational services Significant political, media and stakeholder concern Low defensibility of realisation of risk Reinstatement to pre-risk condition difficult requiring commitment of a high level of resources. |
| Medium (Possible) | Possibility of occurrence in 10 year period or 20% to 50% chance of occurrence. | History of some occurrence. | Financial impact on GLA/GLF likely to be in region of £100K to £500K Moderate impact on GLAs’ delivery of operational services Moderate stakeholder impact/concern National media interest Some defensibility of realisation of risk probable Reinstatement to pre-risk condition possible with the commitment of a moderate level of resources. |
| Low (Remote) | Unlikely to occur in a 10 year period or 10% to 20% chance of occurrence. | Unlikely to occur; low history of occurrence. | Financial impact of GLA/GLF likely to be in the region of £10K to £100K Low impact on GLAs’ delivery of operational services Low stakeholder impact/concern Local media interest Defensibility of realisation of risk likely Reinstatement to pre-risk condition likely to be achieved with the minimum commitment of resources. |
| Very Low (Extremely Remote) | Highly unlikely to occur in a 10 year period or less than 10% chance of occurrence. | Has not occurred; very unlikely to occur. | Financial impact on GLA/GLF likely to be below £10K Very low impact on GLAs’ delivery of operational services Little (if any) stakeholder concern/impact No media interest Excellent prospect of defensibility of realisation of risk Reinstatement to pre-risk condition very likely to be achieved. |