## Slide 1
Channel Markers Project
November 2011 – July 2012
A presentation on
Papua New Guinea

## Slide 2
Summary
Prior to commencement of this project, there were 211 operational AtoNs in PNG waters. Those 211 AtoNs were restored between 2004 and 2011, as part of a series of rehabilitation projects, funded by the Asian Development Bank. Those projects were focused on International Shipping Routes.
The National Maritime Safety Authority realized the need to also focus on the provision of AtoNs for domestic passenger and cargo shipping and small crafts. A strong push from the local shipping industry and isolated communities resulted in the NMSA identifying the need to implement a project to respond to those needs.
The ‘Channel Marker Rehabilitation Project’ was implemented by the National Maritime Safety Authority (NMSA) of Papua New Guinea, to increase the amount of AtoNs in PNG coastal waters, with a specific focus on domestic shipping and small craft.
A total of 63 sites were identified for the project, including the re-commissioning of previous sites and the identification of new sites. The majority of coastal provinces were targeted, with the focus on provinces with reliance on a high volume of local shipping. The sites were established through consultation with the local shipping industry, provincial government and coastal communities around the country.
The NMSA tendered the design and construction of the AtoNs in mid 2011. The tender was awarded to a local contract in late 2011.

## Slide 4
Logistics: 63 sites spread over 8 coastal provinces
1000 miles of sea travel between the furthest sites.

## Slide 5
Implementation - Design
Contract was ‘Design & Construct’ with the only specification by NMSA that all structures be a standard shallow-water pile. This was one to keep all infrastructure standard and to reduce maintenance costs
61 of the 63 sites were identified for short range lanterns. 2 sites were identified as requiring 10nm range.
The concept design identified by the contractor was;
355mm steel pile with marine epoxy paint system.
Sacrificial anode (25 years) and full length denso corrosion protection system.
Stainless steel ladder, driving tongue and pedestal.
Designed for 2 – 3m depth, with a focal height of 7m above SL. Pile penetration = 8m
The design was optimized for;
Quick construction time, reducing time required on site and to reduce impact on the surrounding marine environment.
Focus on minimal maintenance - No exposed mild steel, and robust corrosion protection systems.

## Slide 6
Implementation – Site Assessments
Pre Construction Site Assessments were needed to confirm sites were suitable for the proposed structure. This included identification of the site using GPS coordinates supplied by the client and confirmation of suitability from a navigational perspective. This was a process carried out by the contractor and NMSA officers.
Environmental Assessments were carried out for every site, as most of the sites are located in remote and sometimes pristine marine environments. Marine habitat assessments of the proposed site allowed the contractor to identify any specific environmental concerns at each site and allowed creation of a comprehensive Environmental Management and Monitoring Plan.

## Slide 7
Implementation – Preparation and Mobilization
Site Assessments allowed finalization of the concept design. Materials were ordered and all structural components fabricated in controlled workshop conditions in PNG.
An Environmental Management and Monitoring Plan, and a Safety Management Plan were completed by the contractor and submitted to the NMSA. The plans were reviewed and approved for use.
Construction was carried out by a qualified team aboard a fully self sufficient construction barge. All materials required for all sites was loaded prior to mobilization. Enough stores were on board to maintain an isolated construction program with a crew of 30 people for the expected duration of the project – 3 months.

## Slide 8
Implementation – Construction
Installation of the 63 sites was completed in 66 days, from start to finish.
Specialized equipment, an experienced piling crew, along with a modular and simple pile design, allowed for a very speedy installation.
All sites were checked by divers prior to and after completion of the pile installation process, in order to monitor and document any environmental impact.
The project was completed with no Environmental Incidents. Environmental Management Reports with underwater photographical evidence were submitted for each site.

## Slide 9
A pictorial summary....