IALA GUIDELINES

PRESERVATION OF HISTORIC  LIGHTHOUSES

Funding Options for the Preservation of Historic Lighthouses

INITIAL DRAFT

AISM-IALA : 20 ter rue Schnapper  - 78100 Saint-Germain en Laye  -  France

Telephone : + 33 1 34 51 70 01      -         Telefax : + 33 1 34 51 82 05

E-mail : iala-aism@wanadoo.fr       -      Internet : //www.iala-aism.org

INTRODUCTION

Funding Options for the Preservation Lighthouses

MAP  THE OPPORTUNITIES FOR THE PROJECT

PRODUCE BUSINESS PLAN

REVIEW FUNDING OPTIONS

ASSESS SCALE OF FUNDING REQUIRED

UNDERTAKE PROJECT  JUSTIFICATION

START

SOURCE FUNDING

REVIEW LEGAL CONDITIONS

FINISH

Funding Options for the Preservation of Historic Lighthouses – Consider the following approach to sourcing funding:

CONTENTS

1	mAP THE OPPORTUNITIES FOR THE PROJECT	4

1.1	Scope of the Project	4

1.2	Potential Factors	4

1.3	Commercial potential of the project	4

1.4	Review Public Accessibility	4

1.5	Policy of Conservation	4

1.6	Importance of Site	4

1.7	National Legislation	4

2	PRODUCE A BUSINESS PLAN	4

2.1	Prepare a Business Plan	4

2.2	Creation Costs and Data	4

2.3	Day to Day Costs	4

2.4	Updating and Revitalisation	4

3	UNDERTAKE PROJECT JUSTIFICATION	5

3.1	Prepare Project Justification	5

4	REVIEW AVAILABLE FUNDING OPTIONS	5

4.1	International / European	5

4.2	Government Funding	5

4.3	Regional/Local Government	6

4.4	National (non-government) funding	6

4.5	Commercial Sponsorships	6

4.6	Commercial Operations	6

4.7	Public Sponsorship	6

4.8	Other Funding Options	7

5	ASSESS SCALE OF FUNDING	7

6	SOURCE FUNDING and REVIEW THE LEGAL CONDITIONS	7

ANNEX	8

# mAP THE OPPORTUNITIES FOR THE PROJECT

Scope of the Project

Review potential scope

## Potential Factors

Assess the potential public interest, educational, imagination and historical factors.

## Commercial potential of the project

Look at the straight commercial potential of project

## Review Public Accessibility

Policy of Conservation

Evaluate the project in relation to filling the policy of conservation

## Importance of Site

Review the Local and National level of importance given to the site

## National Legislation

Consider the need for a change in National Legislation  to allow project to go ahead.

# PRODUCE A BUSINESS PLAN

## Prepare a Business Plan

Prepare a business plan considering the whole life of the project based on the scope produced in section 1

## Creation Costs and Data

Research creation costs and possible user/visitor data such as numbers and charges in comparison to ‘similar’ attractions nearby.

## Day to Day Costs

Consider existing day-to-day costs involved in conservation.

## Updating and Revitalisation

Consider issues of updating, modernisation and revitalisation during the project’s life span.

# UNDERTAKE PROJECT JUSTIFICATION

.

## Prepare Project Justification

Prepare a full financial project justification for the project based over a realistic life of 10, 15 or 20years. Include:

### Consider the ‘Do Nothing’ costs associated with existing statuary duties.

### Estimate initial capital expenditure.

Consider daily out goings.

### Estimate income

### Include funding costs.

### Assess consultancy costs

# REVIEW AVAILABLE FUNDING OPTIONS

Funding is available from various sources depending on the nature of the project and Local, National and International arrangements. The following are areas that should be considered and investigated.

## International / European

### UNESCO – World Heritage and Regeneration

Government Funding

### Provide Aids to Navigation

### To support heritage based projects such as museums, which may include Lottery funding

### To promote tourism

### To enhance the local economy and trade

### To provide protection of the environment

### To promote educational aspects

### For Research

### Defence

## Regional/Local Government

### Regional/Local Government would provide funding for similar factors as listed above in 4.1 but in addition :

### Planning Authority can provide supporting grants for the maintenance of Listed Buildings

### Regional Development Agencies can provide funding to support the development of businesses and enterprises as part of employment regeneration

## National (non-government) funding

This would include Charitable Trusts that have their own individual aims and objectives into which the project may fall.

## Commercial Sponsorships

## Commercial Operations

Revenue arising from:

### Renting out property

### Branding and Merchandising

### Allowing public access

### Licensing activities

### Facility fees

### Entering into partnerships

## Public Sponsorship

Funding support may be provided by the General Public through:

### Donations

### Bequests

### Fund raising involving public support such as ‘friends of’, sponsored walks, etc.

## Other Funding Options

### Savings made under current Tax Laws for example covenants where in certain situation previously paid income tax can be reclaimed from the Government

### Disposal of property to allow reinvestment

### Borrowing against assets (mortgaging)

### Consultancy and contractual services

### User charges

# ASSESS SCALE OF FUNDING

Assess the scale of funding required. Small amounts may be obtained by appealing to the public direct, while multi million $ or £ will need to be sought at National Level

# SOURCE FUNDING and REVIEW THE LEGAL CONDITIONS

Once an initial sourcing of funds has been made and the necessary contacts have been made the appropriate applications have to be made. The aim is to convince those administering the funding that it meets their relevant criteria and objectives, has a sound business plan accompanied, where necessary with a sound financial justification. The provision of funding particularly in the form of grants will have certain condition attached covering in particular the closure or failure of the venture, which may have serious financial implication on those involved. Those sponsoring such applications should fully consider the consequences of such conditions.

# ANNEX

CHECK LIST

The following provides an aid to check that all points have been considered.

| Items that have to be Considered | Is Item Applicable? Yes/No | Considered () | Comments |
| --- | --- | --- | --- |
| Map the Opportunities |  |  |  |
| Produce the Business Plan |  |  |  |
| Project Justification |  |  |  |
| Review Funding Options |  |  |  |
| International |  |  |  |
| - Government |  |  |  |
| - Regional |  |  |  |
| - Commercial |  |  |  |
| - Commercial sponsorship |  |  |  |
| - Commercial Operations |  |  |  |
| - Public Sponsorship |  |  |  |
| - Other Funding Options |  |  |  |
| Assess Scale of Funding |  |  |  |
| Legal Implications |  |  |  |
| Source Funding |  |  |  |