IALA EEP COMMITTEE - DETAILED WORK PROGRAMME – 2002 TO 2006

WG1 – Fixed & floating support structures and power systems - Chairman: A. Wilkins

| Item no. | Original Task no. | Title | Objectives | Work to be undertaken | Work Sessions | Expected completion | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| # 1.1 | 2 | Develop Guidelines on maintenance practices for buoys and small fixed Aids to Navigation structures, including signal equipment | - Identify and share information on cost effective maintenance practices, new processes and new materials - Produce guidelines | - Use expertise within the committee to identify relevant areas and produce a questionnaire to identify world wide practices that may be incorporated in the final guideline. - Collate the results of the questionnaire into individual topic reports. - Design, write and edit the final guide. | # 6 | EEP6 |  |
| # 1.2 (also refer to 5.1.4) | 8 | Develop Guidelines on the technical aspects of the maintenance of lighthouses | - Divide structures into groups such as construction materials, sites and navigational use - Further divide into historic and maintenance considerations. | - In conjunction with WG5: - Identify areas of expertise required to produce guidelines - Define objectives for a workshop to produce specific sections of the guidelines - Prepare workshop. (See Task 12) - Forward draft guidelines resulting from workshop and committee input to Council for approval. | # 4 | EEP7 |  |
| # 1.3 | M4 | Monitor developments in renewable energy sources. | - Assess new developments, potential applications and the cost effective use of renewable energy sources. - Update relevant Guidelines. | - Monitor, collect and collate information on new developments, potential applications and the cost effective use of renewable energy sources, particularly: - Fuel cells - Wind & Wave Generators - Solar photovoltaic - Report on technical information as it becomes available | # Ongoing | Report to full committee through rapporteur process. |  |

WG1 – Fixed & floating support structures and power systems - Chairman: A. Wilkins

| Item no. | Original Task no. | Title | Objectives | Work to be undertaken | Work Sessions | Expected completion | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1.4 | M2 | Monitor developments in AtoN support structures and other equipment, excluding light and colour | - Assess potential applications and the cost effective use of new AtoN equipment | - Collect and collate information on new AtoN equipment particularly: - Report on as technical information becomes available | Ongoing – report to full committee through rapporteur process. |  |  |
| 1.5 | 15 (Council Report Session 27) | Revise Guidelines on battery handling and maintenance | - Integrate existing guidelines on: - the safe handling of batteries, and - maintenance and Operation of Batteries | - Carry-out Intersessional work to create draft of integrated guideline. - Review of draft guideline at EEP2. | 3 | EEP3 |  |
| 1.6 | 16 Carry forward from ENG 16 | Provide guidance on the practicability of a universal IALA Solar Design program based on functional specification | - Review examples of basic solar sizing programs - Determine practicality of creating a universal Solar Design Computer Program - Create a universal Solar Design Computer Program (if feasible) | - Ask all members to bring examples of basic solar sizing programs to EEP2. - Review feasibility of program at EEP2 and determine if work will proceed. | 3 | EEP4 |  |

WG1 – Fixed & floating support structures and power systems - Chairman: A. Wilkins

| Item no. | Original Task no. | Title | Objectives | Work to be undertaken | Work Sessions | Expected completion | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| # 1.7 |  | # Develop subject matter for a workshop in conjunction with WG 5 – refer to item 6 in this regard |  |  |  |  |  |
| # 1.8 | N/A | # Other items as they may arise |  |  |  |  |  |
| # 1.8.1 |  | Consider and prepare reply re. inquiry from Chilean Lighthouse Service articulated buoys |  |  | # 1 | Completed at EEP1 |  |

Sessions

| Item | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.1 | ■ | ■ | ■ | ■ | ■ | ■ | ■ |  |
| 1.2 |  |  |  | ■ | ■ | ■ | ■ |  |
| 1.3 |  |  |  |  |  |  |  | Monitor Item - ongoing |
| 1.4 |  |  |  |  |  |  |  | Monitor Item - ongoing |
| 1.5 | ■ | ■ | ■ |  |  |  |  |  |
| 1.6 | ■ | ■ | ■ |  |  |  |  |  |
| 1.7 | ■ | ■ | ■ |  |  |  |  |  |

WG2 – Quality Assurance, Availability and Certification - Chairman: C. Baker

| Item no. | Original Task no. | Title | Objectives | Work to be undertaken | Work Sessions | Expected completion | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2.1 | 6 | Revise Guidelines on Quality Assurance, Availability of systems and components | - Provide the membership with up to date information on Quality Assurance, Availability and Reliability issues pertaining to AtoN systems and components. - Maintain present Guidelines in an updated condition, taking into consideration new techniques being developed by member Authorities and the International community - Continue making member Authority’s specifications available. - Obtain information on member’s testing and performance measuring facilities with the intention of facilitating co-operation | - Revise IALA Guide to the availability and reliability of aids to navigation - Review and produce relevant documentation on availability and reliability techniques, objectives, levels and related issues - Prepare specification templates for aids to navigation systems and components. - Arrange a questionnaire to determine the testing and performance measuring facilities of Members and compile a database to be linked to the IALA web site. - Produce articles for the IALA bulletin on this subject | 4 | EEP4 |  |

WG2 – Quality Assurance, Availability and Certification - Chairman: C. Baker

| Item no. |  | Original Task no. | Title | Objectives | Work to be undertaken | Work Sessions | Expected completion | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2.2 |  | 7 | Develop Guidelines on the Methodology of collecting information on reliability and failures of AtoN equipment | - Provide the membership with up to date information on how to collect information on reliability and failures of AtoN equipment | - Draft Guidelines making keeping in mind ENG16/8/10, using Trining House document as a template. | 4 | EEP7 |  |
| 2.3 |  | M5 | Monitor the development of the IALA equipment certification process | - Contribute towards Equipment Certification as and when required | - Contribute towards Equipment Certification as required. - Prepare product specification templates. | Ongoing |  |  |
| 2.4 |  | 13 (2002 IALA Conference Recommen-dations) | Revise the guidelines on AtoN Training | - Maintain and update the IALA Guidelines on AtoN Training. | - Utilise the expertise within the Committee to review each part of the guidelines | 3 | EEP7 |  |
| 2.5 | N/A |  | Other items as they may arise |  |  |  |  |  |

WG2 – Quality Assurance, Availability and Certification - Chairman: C. Baker

# Sessions

| Item | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2.1 | ■ | ■ | ■ | ■ |  |  |  |  |
| 2.2 |  | ■ | ■ | ■ | ■ |  |  |  |
| 2.3 | ■ | ■ | ■ | ■ | ■ | ■ | ■ |  |
| 2.4 |  | ■ |  |  |  | ■ | ■ |  |

# WG 3 - Environment And Publications Chairman – R. Beauchesne

| Item no. | Original Task no. | Title | Objectives | Work to be undertaken | Work Sessions | Expected completion | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.1 | 1 | Develop Guidelines on environmental considerations on AtoN engineering | - To raise the profile of environmental issues in the AtoN community - To produce a “Green Guide” to AtoN operation, including how to dispose of batteries and other hazardous material | - Design and circulate a questionnaire on local legislation and environmental considerations - Collate questionnaire responses - Design, write and edit Guides | 7 | EEP7 |  |
| 3.2 | 5 | Review and update relevant sections of the NAVGUIDE | - To keep the NAVGUIDE updated on engineering issues. - Keep relevant documentation under review and update as and when required, e.g. dictionaries | - Review all relevant NAVGUIDE chapters from an Engineering Committee’s perspective and produce any new and/or revised text for inclusion in the next version of the NAVGUIDE: - Review relevant documentation and update where necessary |  | EEP5 |  |
| 3.3 | M1 | Monitor the development of computer methods and applications to simplify design and management of AtoN | - To identify computer programmes and methods used by AtoN operators - To make this information available to the IALA membership | - An annual questionnaire will be circulated to the membership; the information will be collated annually culminating in: - Produce a report and circulate it before the next Conference - Monitor availability of new computer programmes | Ongoing | Report to full committee through rapporteur process. |  |

# WG 3 - Environment And Publications Chairman – R. Beauchesne

| Item no. |  | Original Task no. | Title | Objectives | Work to be undertaken | Work Sessions | Expected completion | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3.4 | N/A |  | Other items as they may arise |  |  |  |  |  |

###### Sessions

| Item | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3.1 | ■ | ■ | ■ | ■ | ■ | ■ | ■ |  |
| 3.2 | ■ | ■ | ■ | ■ | ■ |  |  |  |
| 3.3 | ■ | ■ | ■ | ■ | ■ | ■ | ■ |  |
| 3.4 | ■ | ■ | ■ | ■ | ■ | ■ | ■ |  |

WG 4 - Light and colour – Chairman - O. Ericsson

| Item no. | Original Task no. | Title | Objectives | Work to be undertaken | Work Sessions | Expected completion | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 4.1 | 3 | Develop Guidelines on ambient light levels at which AtoN lights should switch on and off | - Produce a definitive Guideline on this subject | - Obtain standards developed by Lighthouse Authorities - Obtain the opinion of technical experts - Achieve consensus within the Committee - Design, write & edit Guide | 4 | EEP5 |  |
| 4.2 | 4 | Develop Guidelines on sectors, sector lights and sector projection lights | - Provide information on the different types of sector projectors, their advantages and disadvantages, equipment availability and guidance on installation - Produce Guidelines | - Collate information on commercial sector projectors - Obtain specialist information on incorporating sectors in lanterns and fixed lenses - Edit information - Design, write and edit Guide |  | EEP6 |  |
| 4.3 | 14 (2002 IALA Conference Recommen-dations | Study the spectral and spatial characteristics of new and developing new lights, in particular LED’s with the view of informing the IALA Membership and to update relevant IALA documentation | - Provide the Committee and the membership with relevant and updated information on this topic | - Study the operating characteristics of LEDs and other light sources, including the vertical divergence and the variance in angular intensity, when used as AtoN light sources - When appropriate, review applicable IALA Recommendations and Guidelines - Write articles for the IALA bulletin on the subject | 6 | EEP7 |  |

WG 4 - Light and colour – Chairman - O. Ericsson

| Item no. |  | Original Task no. | Title |  | Objectives | Work to be undertaken | Work Sessions | Expected completion | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 4.4 |  | M3 | Monitor international progress on colours of light signals, calculations of the effective intensity of flashed lights and the determination of luminous intensity |  | - Ability to update IALA Recommendations in these areas - Update relevant IALA Recommendations and standards - Address Blue Light as required and incorporate in relevant Recommendations and Guidelines | - Create a specialist Working Group - Liase with relevant technical specialists and international committees - Use the information to design, write & edit new recommendations and standards to supersede;, review and update if need be: - Draft a Recommendation for the Calculation of Effective Intensity (1980) - Draft a Recommendations for Colours of Light Signals - Draft a Recommendation on Luminous Intensity - Draft a Recommendation on Photometry | Ongoing | Report to full committee through rapporteur process. |  |
| 4.5 |  | M2 |  | Monitor developments in AtoN | - Access potential applications and the cost effective use of new visual AtoN equipment - Write a report or guide on each new type of equipment | - Collect and collate information on new visual AtoN equipment particularly: - The use of low power directly projected Laser leading lights - The operating characteristics of LED’s when used as AtoN light sources - Maitnain and update as necessary the “Guidelines on new Light Sources and associated Power Supplies“ - Report as technical information becomes available | Ongoing | Report to full committee through rapporteur process. |  |
| 4.6 | N/A |  |  | Other items as they may arise |  |  |  |  |  |

WG 4 - Light and colour – Chairman - O. Ericsson

###### Sessions

| Item | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 4.1 | ■ |  | ■ | ■ | ■ |  |  |  |
| 4.2 | ■ | ■ | ■ | ■ |  |  |  |  |
| 4.3 |  | ■ | ■ | ■ | ■ | ■ | ■ |  |
| 4.4 | ■ | ■ | ■ | ■ | ■ | ■ | ■ |  |
| 4.5 |  | ■ | ■ | ■ | ■ | ■ | ■ |  |

# WG 5 - Preservation Of Historic Lighthouses And Aton - Chairman: L. Wilson

| Item no. | Original Task no. | Title | Objectives | Work to be undertaken | Work Sessions | Expected completion | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 5.1 | Further develop Preservation Manual to include chapters on: |  |  |  |  |  |  |
| 5.1.1 | 9 | Funding options for the preservation of historic lighthouses | - Provide guidance on how to assess opportunities to obtain funding for the preservation and maintenance of historic lighthouses | - Design, edit and produce guidance - Review existing Preservation Manual and include new chapter - Issue updated edition of the Guide | 4 | EEP4 |  |
| 5.1.2 | 10 | Means to record and document changes in the history of lighthouses | - Indicate the importance of the documentation of lighthouse history and to give guidance on: - Where existing documentation is to be found - How to record the development of changes in lighthouse history - How documentation should be managed. | - Design, issue and review questionnaire on retention and control of historic documentation - Design, edit and produce guidelines on documentation of lighthouse history - Review existing manual to incorporate chapter on documentation of lighthouse history | 5 | EEP6 |  |

# WG 5 - Preservation Of Historic Lighthouses And Aton - Chairman: L. Wilson

| Item no. |  | Original Task no. | Title | Objectives | Work to be undertaken | Work Sessions | Expected completion | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 5.1.3 |  | 11 | Managing the consequences of technical changes | - Provide guidance to authorities on how to manage the introduction of new AtoN technology while preserving the historic lighthouse. | - Design, edit and produce guidelines on the introduction of new AtoN while preserving historic lighthouse - Review existing manual to incorporate a chapter on the introduction of new AtoN while preserving historic lighthouse - Review technical options and their implications to historic lighthouse preservation. | 5 | EEP6 |  |
| 5.1.4 (also refer to 1.2) |  | 8 | Technical aspects of the maintenance of historic lighthouses in conjunction with WG1. | - Refer to 1.2 | - Refer to 1.2 |  |  |  |
| 5.1.5 |  |  | Do’s and don’ts of Preservation of AtoN |  |  | 4 | EEP6 |  |
| 5.2 |  | 12 | Develop an IALA web site portal relating to historic lighthouses for public relations purposes | - Encourage public awareness by initiating a facility enabling member countries to display information on their historic lighthouses | - Review previous work and interface with new IALA website - Carry out interactive template trials - Promote member country participation in recording data | 5 | EEP7 |  |
| 5.3 |  |  | Develop subject matter for a Workshop in conjunction with WG 1 – refer to item |  |  |  |  |  |
| 5.4 | N/A |  | Other items as they may arise |  |  |  |  |  |

# WG 5 - Preservation Of Historic Lighthouses And Aton - Chairman: L. Wilson

###### Sessions

| Item | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 5.1.1 | ■ | ■ | ■ | ■ |  |  |  |  |
| 5.1.2 | ■ | ■ | ■ | ■ |  | ■ | ■ |  |
| 5.1.3 | ■ | ■ | ■ | ■ |  | ■ |  |  |
| 5.1.4 | Refer to 1.2 |  |  |  |  |  |  |  |
| 5.1.5 |  |  | ■ | ■ | ■ | ■ |  |  |
| 5.2 | ■ | ■ | ■ | ■ |  | ■ | ■ |  |

6 - Prepare and convene a Workshop

| Item no. | Original Task no. | Work to be undertaken | Work Sessions | Expected completion | Comments |
| --- | --- | --- | --- | --- | --- |
| 6.1 |  | Develop subject matter, objectives and title of proposed Workshop |  |  |  |
| 6.2 |  | Finalise arrangements |  |  |  |

# EEP 1 – October 2002 EEP 4 – April 2004 EEP 6 – April 2005 # EEP 2 – April 2003 EEP 5 - October 2004 EEP 7 – October 2005 # EEP 3 – October 2003

## Each WG is requested to consider all the above mentioned tasks and:

## If necessary, produce a summary of the WG’s understanding of the assignment(s), to assist all members to have a clear understanding thereof.  This can also be used as a future Terms of Reference (TOR) for the assignment.

## Prioritise the tasks

## Confirm the end results

## Review work programme and confirm the target dates

## Provide an action plan to meet the end results and target dates

## Produce report and working papers for discussion in the plenary sessions