Project Proposal

IALA e-learning Portal and basic courses

Prepared for:

IALA Council,

Session 34

2nd  Draft – May. 2004

Prepared by:

J. Carson-Jackson,

IALA Technical Coordination Manager

Table of Contents

Background - What is ‘e-learning’?	3

Goal – IALA and e-learning	3

Considerations – Rooted in IALA Strategy	3

Dimensions – Assets and Barriers	3

Process – Initiating and Maintaining	4

6 Steps to Creating an IALA e-learning Portal	5

Action Plan Step 1 – Identify Scope	10

Status Report – May 2004	11

Internet Review	11

Contact with existing, similar sites	13

Nautical Campus (url - http://www.nauticalcampus.org/)	13

Maritime e-Campus (url - http://www.maritime-ecampus.com/)	13

IALA and e-learning –

# Background - What is ‘e-learning’?

“e-learning” is learning that occurs through a variety of electronic media.  Learning may take place in a traditional learning environment (college, university, school), through distance, or both.  Elements of e-learning can include:  Simulations (computer based, partial, full mission); WBT (Web Based Training); CBT(Computer Based Training); computer conferencing; video conferencing; CSILE (Computer Supported Intentional Learning Environments); etc.

E-learning in MET (Maritime Education and Training) is becoming available and practical.  A number of Maritime Training Institutes are offering on-line courses, industry is providing on-learning training solutions, and employees are beginning to demand more flexible training options.  .

# Goal – IALA and e-learning

- To provide IALA membership with an access point for training on aspects related to Aids to Navigation.  (e-learning Portal)

- To provide training opportunities to IALA membership on aspects related to Aids to Navigation, which do not exist elsewhere.  (e-learning modules)

# Considerations – Rooted in IALA Strategy

The creation of a virtual IALA community e-learning portal, will demand specific review of the international maritime environment in which IALA is positioned.  These include strategic factors that IALA has identified:

- Interdependence of all aspects of transportation modes (requirement for a holistic approach)

- Emphasis on standards – both ashore and afloat

- Developments in technology

Other factors that must be considered in the development of an e-learning portal and basic courses are the users of the site and the means of tracking use / learning (learning management system or LMS).

# Dimensions – Assets and Barriers

Specific dimensions of the e-learning portal project include:

### Drivers within the Industry

- for example the level and availability of existing AtoN related training.  The e-learning portal project could provide a means to increase access to training options.

### Stakeholders

- for example, IALA Members – both National and Industrial.  From the National Member perspective, the portal could provide a means of identifying training options, promoting training programs and participating in training; from the Industrial Member perspective, the portal could be a means of promoting existing training, developing additional training, linking to ‘problem solving’ just-in-time training, providing value added service to their product through their association with IALA.

### Content

- for example, existing AtoN training content to be identified for possible transfer to the e-learning environment; portal to link to existing AtoN training programs.

### Technology

- for example, identification of cross-platform technology to allow for maximum access, identification of security issues (firewalls, encryption) that need to be resolved, intellectual property rights and other legal issues that may need to be resolved.

### Learners

- for example – geographic location, access to technology, level of comprehension of technology, requirements for cultural and language adaptations.

### Tracking

- for example, a means to register and track courses / use of site.  For the actual courses, a means of measuring progress will need to be defined.

# Process – Initiating and Maintaining

In order to provide the information required in a timely and cost effective manner, a process is suggested that will entail six main steps:

- Identify scope for IALA e-learning portal, including needs analysis;

- Establish Framework for IALA e-learning portal;

- Design web-portal (Identifying and implementing cost effective software solution for e-learning portal, including, as necessary, the following elements:  Learning Management System, security encryption, etc.);

- Implement IALA e-learning portal;

- Manage creation of content (as required) for IALA e-learning courses;

- Monitor use, adjust as necessary (on-going).

Please note that, following the initial needs analysis, actions/steps may be carried out in a synchronous manner to enable a cost/time effective approach to the project.

## 6 Steps to Creating an IALA e-learning Portal

The steps in the process can be further defined into specific action items.  These steps follow closely the requirements as identified in various e-learning white papers, as well as making use of Stufflebeam’s CIPP (Content, Input, Process, Product) evaluation model.

| Content (What needs to be done?) | Step 1 – Identify Scope |
| --- | --- |
| Input (How should it be done?) | Step 2 – Establish Framework Step 3 – Design portal |
| Process (Is it being done?) | Step 4 – Implement Portal Step 5 – Manage creation of content |
| Product (Did it success?) | Step 6 – Monitor use, adjust as necessary |

| #### Step 1: Identify scope for IALA e-learning portal |  |  |
| --- | --- | --- |
| #### Action | #### Process | #### Expected Outcomes |
| Research Review / Review of existing, similar sites. | Document search – web based. Contact existing, similar sites. | Overview of ‘best practices’. Indication of successes / difficulties in setting up sites. Indication of site use / users. |
| Needs analysis for introducing an e-learning portal for IALA membership. | Electronic survey from IALA public web site. Insert in IALA bulletin for membership comment. Include in IALA Committee Questionnaire. | Indication of support / non-support for project. Indication of project team members. |
| Critical Milestone - Clarification of project (go / no go for project). |  |  |

| #### Step 2: Establish Framework for IALA e-learning portal |  |  |
| --- | --- | --- |
| #### Action | #### Process | #### Expected Outcomes |
| Contact IALA members offering maritime / AtoN related e-learning (portals and courses) and familiarize them with the IALA e-learning portal project (if required). | e-mail contact with introduction letter and copy of approved project plan | Re-alignment of project to respond to members comments / needs. (updated project proposal / plan) |
| Develop IALA e-learning Portal Philosophy | Discuss aspects of e-learning portals with project team members; Prepare input for Council on philosophy for portal (i.e. level of security; available free to members, cost to non-members; | Clarification of IALA e-learning portal protocols and implementation. Continuing Council support for project. |
| Familiarize project team with existing maritime / AtoN related e-learning courses / portals | Refer to document and internet review. | List of existing portals, List of AtoN related e-learning courses; List of contacts; List of AtoN related training that does not have an existing e-learning program. |
| Identify subject for pilot e-learning module development. | Review list of AtoN related training that does not have existing e-learning program | Create training objectives, enabling objectives and detailed curriculum. Create basic story board for content. Identify tools that may be required to create content. |

| #### Step 3: Design IALA web-portal |  |  |
| --- | --- | --- |
| #### Action | #### Process | #### Expected Outcomes |
| Identify options for e-learning portal | Internet / document review to carry identify best-practices. Analysis of options. Identification of three choices for e-learning portal management for Council review. | List of options for e-learning portal management. Status report on project for IALA Council. |
| Create MOUs, as required, with IALA members offering maritime / AtoN related e-learning for inclusion in IALA e-learning portal. | Develop MOU in conjunction with membership. | List of portals / courses to post on initial IALA e-learning web portal. Revised list of courses requiring development. Table of options for development of applicable courses not yet in e-learning format. |
| Develop content for e-learning Pilot module. | Refer to best practices, use existing approaches to supplement approach. | Pilot e-learning module to include on site. |

| #### Step 4: Implement e-learning Portal |  |  |
| --- | --- | --- |
| #### Action | #### Process | #### Expected Outcomes |
| Implement chosen e-learning portal | Purchase portal software as required; Identified project team members to learn portal management Populate portal with identified course / site links. | IALA e-learning portal on the web. |
| Monitor use of e-learning portal. | Close monitoring for first 60 days, reduced level of monitoring thereafter. Full analysis of use after 6, 12 and 18 months. | Identification of use of portal. Identification of trends in use of portal. List of options regarding the trends. |

| #### Step 5: Manage Creation of e-learning Content (as required) |  |  |
| --- | --- | --- |
| #### Action | #### Process | #### Expected Outcomes |
| Create e-learning content as required. | Prioritize content development. Develop training objectives and enabling objectives for priority items. Develop course outline (description of structure and sequence of instruction) Develop lesson plans and instructional materials | e-learning modules available for use. . |

| #### Step 6: Monitor use, adjust as necessary (ongoing) |  |  |
| --- | --- | --- |
| #### Action | #### Process | #### Expected Outcomes |
| Identify best evaluation process for IALA e-learning web portal. | Identify what and how to monitor / evaluate site. Create evaluation / monitoring process that meets all levels of evaluation as per Kirkpatrick: - Reaction - Learning - Behaviour - Results | Updates on portal activity; Clarification of needs / objectives; Identification of possible improvements. |
| Monitor site | Spot checks of site. Formal review of site use at specified intervals. | Identification of site use / ongoing support of site. Identification of amendments required / updates. Clarification of further content requirement / content no longer required. |

# Action Plan Step 1 – Identify Scope

| Proposed Activity | ##### Proposed Dates | ##### Time / effort |
| --- | --- | --- |
| Research Review / Review of existing similar sites |  |  |
| Internet search for other e-learning portals | March – May 2004 | 3 days |
| Listing of e-learning portals | May 2004 | .5 day |
| Identification of marine e-learning portals | May 2004 | .5 day |
| Contact web-masters of marine related e-learning portals – clarify start up process; successes/concerns; level of satisfaction. | May – June 2004 | 2 days |
| Identify existing IALA members with e-learning portals. | May – June 2004 | 1 day |
| Needs analysis for introducing an e-learning portal for IALA membership. |  |  |
| Create introduction for project to include in releases; presentations, etc. | August 2004 | 1 day |
| Create format for electronic survey process from IALA public web site. | September 2004 | 2 days |
| Include introduction to project, survey request in IALA Bulletin. | September 2004 | .5 day |
| Analyze results from survey. | November 2004 | 2 days |
| Prepare update for Council, including suggested go / no go for remainder of project. | December 2004 | 1 day |

Depending on the result of the survey, a more complete time-line will be presented to Council Session 35 for approval.

Annex

# Status Report – May 2004

# Internet Review

A learning portal is a site with a search engine that is usually customized to provide specific topics of information which is presented in a variety of ways, for example, in on-line libraries, newsgroups, newsletters, various web sites, etc. (http://www.mapnp.org/library/trng_dev/methods/on_line.htm)   For the purposes of the IALA e-learning portal, the site would provide a listing of existing courses as well as the possibility to host specific modules for learning purposes.  An aim of the site would be to promote development and harmonization of AtoN training.

Brandon-Hall (http://www.brandon-hall.com/brandon-hall/) is a leader in e-learning portals.  Many references from this site were used in the initial web and document review.

In ‘Corporate Learning Portals’, by Jay Cross, the benefits of a learning portal are identified as (adapted for IALA e-learning context):

- Accelerate learning, less holdup between learning and action, puts downtime to good use, just in time learning for repairs of AtoN equipment;

- Leverage best practice knowledge enterprise wide;

- Provide access to all learning opportunities and advice from one virtual location;

- Single-source of learning for functions (could be of import for industrial members selling similar products internationally);

- Provides home base for communities of practice;

- Integrates disparate functions, dissolves cognitive boundaries between different functions, harmonizes approaches to similar functions;

- Moves learning to the learner;

- Resides prominently or the learner's desktop, portable or hand-held;

- Links learner directly to business.

The Learnativity website (http://www.learnativity.com/) provides an overall view of portals, portal technologies and strategies.  For a listing of commercial portals, visit http://www.learnativity.com/learningportals.html .

A review of existing e-learning portals on the internet was carried out between April / May 2004.  The following is a sampling of the sites found.  Please note that this list is not exhaustive, and provides only one or two links per category.  The Categories searched were International, National, Non-Profit, Non-Governmental, Academic, Commercial and Marine.  The search engine used was ‘Dogpile’, a meta-search engine found at www.dogpile.com.  Key search words included ‘e-learning’, ‘portal’ and the specified category.

### International

Unesco e-learning portal

http://www.unesco.org/education/portal/e_learning/Events/Learntec_2001/The_Report/index.shtml

### National

Industry Canada

http://www.cchrei.ca/elearn/

### Non-Profit Organizations

Non-profit Portal

http://nonportal.org/

### Non-governmental Organization (NGO)

The First Palestinians NGO Portal

http://www.palestine-ngos.net/training.asp

### Academic

UCLA on-line

http://www.principalportal.net/module_principal_portal/master_resource.html

### Commercial

Principal Portal e-learning

http://www.principalportal.net/module_principal_portal/master_resource.html

Site4Learning

http://www.site4learning.com/

### Marine

The search focused on marine related e-learning portals.  Please note that the USCG Portal appeared under both the National and Marine searches.

US Department of Homeland Security – E-Learning Links

http://www.cgaux.info/g_ocx/training/e-learning.html

Nautical Campus  (Nautical Institute)  (contact – Julie Lithgow)

http://www.nauticalcampus.org/

Maritime e-campus Kongsberg (Industrial Member) (contact – Serge Cote)

http://www.maritime-ecampus.com/

### Age Specific

While not a specific search category, this site appeared many times.

Third Age (for Seniors)

http://www.thirdage.com/learning/

# Contact with existing, similar sites

## Nautical Campus (url - http://www.nauticalcampus.org/)

The aim of the Campus is to provide the maritime industry with a comprehensive source of guidance for through life career management, the cornerstone of this project will be a database of all maritime related training and educational opportunities for those in the marine industry.  The Nautical Campus is a not-for-profit service that is entirely free to use.  The aim of the Nautical Institute is that Nautical Campus will become the best and most widely used resource for bringing together those seeking maritime courses and those providing it.  Through this process, the Nautical Institutes hopes to foster professionalism within the industry. (adapted from the home page of the Nautical Campus web site)

Julie Lithgow was unavailable, however Julian Parker provided insights into the process of creating Nautical Campus.  Of particular interest was the fact that the site appears to provide resources for trainers and training managers more so than students.  This is likely due to the fact that the students follow a course at a specific maritime institute and then create links to that particular institute and its affiliates.  However, there are instances when a student will identify a course that is available in a specific area, as well as identifying STCW compliant courses.

Main costs were realized during initial start-up, however there is an ongoing maintenance cost for server space and personnel support.  The concept was not to realize any monetary gain from the site, rather it was to provide a service by the Nautical Institute to encourage mariner education and training.

## Maritime e-Campus (url - http://www.maritime-ecampus.com/)

The initial aim of maritime e-campus was to provide a complete solution for the e-learning concept.  The site provides links to a full campus style learning area, including a built in learning management system (LMS).  Maritime-eCampus states that it was the first maritime e-learning portal, combining high fidelity simulation software with complete courseware to provide an effective e-learning training solution for advanced distance learning.

Serge Cote, of KMSS, indicated that the site was more active in the beginning than it is now.  When it first opened, most training institutes did not possess an e-learning solution ‘in-house’ and the portal, complete with an LMS, was quite desirable.  Now, as institutes move towards a ‘blended’ approach, using both e-learning and tradition classroom / simulator delivery, they are purchasing their own LMS systems and have less need for the portal.  Also, the institutes tend to deal at a local or national level rather than an international level as initially expected.

Overall, the portal provided an excellent first step into the e-learning environment, however it is being used less and less.  Training institutes tend to have their own systems, concentrating on their on-site students or on post-training support / career development for past students.  KMSS is concentrating on their e-learning tools with regards to simulation, including the development of simulation content and increasing use of ‘e-coach’.  The portal may become of greater value in the future when institutes begin to actually train at an international level.

Adapted from E-Learning Guidebook, by the Staff of Brandon-hall.com, 2001